## README
Cropfort — Coffee Field OS Template (Plain, Farm-Agnostic)
Purpose
This is Cropfort's own standard operating template — blank, reusable for any farm on the platform. It is not specific to any owner, manager, or field operator; those identities are filled in when the template is instantiated for a real farm. The activity taxonomy (Tier 1 Core / Tier 2 Projects / Tier 3 Interventions) is Cropfort's own product standard and stays in the template as-is.
Sheet Map, in the order they are used
Activity List
The full activity taxonomy, tier-tagged. Add, edit or re-tier activities here — every other sheet reads from this.
Master
Farm name, Term Start Date (drives every date on the workbook), and the block registry — hectares, variety, planting date, tree count. Fill this in first.
Benchmark Rate Survey
Two-adjacent-farm rate survey per activity. Lock the survey once entered; the average shows as a light-shade recommendation; override it and route for approval by the mandated person at the owning company. Approved rates feed the Labor Rate Card directly.
Labor Rate Card
Final piece rate per activity: Benchmark Approved Rate if one exists, otherwise mandays-norm x wage rate entered directly.
Material Rate Card
Standing price list for material inputs.
Outsourced Services Rate Card
Standing indicative price list for third-party services.
Fee Schedule
What the farm owner pays Cropfort's manager — separate from the farm's own operating costs. Confirmed (Core) and Elective (Tier 2/3) lines, each elective with its own activation month, spread over a 3-year, 36-month vision.
Annual Election
Elect activities for the year. Tier 1 has a Core bundle tick electing all at once, overridable row by row; Tier 2/3 have no bundle and no default — elected one by one, only after the commercial agreement for that work is settled outside the platform. Assign a Planned Duration in days to narrow the default seasonal window.
Activity Plan
Magnitude of work per block: tick (read from Election) and Planned Qty, the actual quantity needed. Drives every cost sheet.
Supervisor Progress
Weekly % complete against Planned Qty, resting on the daily Field Ticket record. Automatic shortfall rollover at window close; a stall flag after two consecutive weeks with no movement.
Labor Budget / Material Budget / Service Budget
Cost rollups from the Activity Plan, by block and tier.
Monthly Cost Summary
Materials and services spread across the months each activity's window touches — an honest monthly figure, not fabricated daily precision.
Weekly Cash Flow
The farm owner's cash-planning dashboard: real weekly labor cost plus each month's input/service cost split evenly across that month's weeks. Sized to help plan how much needs to sit in the Project Account.
Total Budget Summary
The farm's own operating cost total, by block and by tier.
Calendar - Block 1
365-day view for this block. Shading is live conditional formatting reading the Annual Election sheet — one tab like this per block.
Monthly Client Report
The client-facing monthly report template: executive summary, progress vs. plan, budget vs. actual, risk register, look-ahead, field observations, and a standing assurance note under the Cropfort Process Assurance Protocol™, distinguishing the manager's own dashboard from independently verifiable facts.
Color Legend
Blue text on yellow fill = required input, not yet filled in.
Black text on light blue fill = a suggested/recommended figure (e.g. the benchmark average) — read it, then decide.
Green text = formula link pulled from another sheet. Do not overtype.
Grey fill = locked/historical once approved.
What this template deliberately does not do
1. It cannot generate a new block's Calendar tab or Election rows on its own when a row is added to Master — plain formulas can't create new sheets or rows; ask for the workbook to be regenerated, or copy the existing block's tabs and repoint the formulas.
2. It cannot truly lock a cell after Benchmark survey data is entered — 'Survey Locked' is a documented convention, not enforced protection. Apply Excel's own sheet protection to those columns if hard enforcement is needed.
3. Rollover in Supervisor Progress calculates the shortfall and flags it; it does not create the follow-up plan entry automatically — that still needs a new Election/Activity Plan row added by hand.
4. The Monthly Client Report's narrative fields are placeholders for a person (or an AI drafting pass a person reviews) to fill in — the sheet does not write prose on its own.

## Activity List
Activity ID | Tier | Category | Activity Name | Unit of Measure | Source / Notes | Default Tick
T1-001 | Tier 1 — Core Services | Nursery | Land Clearing | ha | Cropfort Core Services standard | Y
T1-002 | Tier 1 — Core Services | Nursery | Tree Felling | ha | Cropfort Core Services standard | Y
T1-003 | Tier 1 — Core Services | Nursery | Soil Heaping | m3 | Cropfort Core Services standard | Y
T1-004 | Tier 1 — Core Services | Nursery | Polytube Cutting | kg | Cropfort Core Services standard | Y
T1-005 | Tier 1 — Core Services | Nursery | Polytube Filling | seedling | Cropfort Core Services standard | Y
T1-006 | Tier 1 — Core Services | Nursery | Seedbed Preparation | bed | Cropfort Core Services standard | Y
T1-007 | Tier 1 — Core Services | Nursery | Polytube Arranging | bed | Cropfort Core Services standard | Y
T1-008 | Tier 1 — Core Services | Nursery | Seed Sowing | bed | Cropfort Core Services standard | Y
T1-009 | Tier 1 — Core Services | Nursery | Mulch Material Preparation | bed | Cropfort Core Services standard | Y
T1-010 | Tier 1 — Core Services | Nursery | Mulch Application | bed | Cropfort Core Services standard | Y
T1-011 | Tier 1 — Core Services | Nursery | Shade Material Preparation | bed | Cropfort Core Services standard | Y
T1-012 | Tier 1 — Core Services | Nursery | Shade Construction | bed | Cropfort Core Services standard | Y
T1-013 | Tier 1 — Core Services | Nursery | Mulch Removal | bed | Cropfort Core Services standard | Y
T1-014 | Tier 1 — Core Services | Nursery | Nursery Weeding | bed | Cropfort Core Services standard | Y
T1-015 | Tier 1 — Core Services | Nursery | Shade Thinning | bed | Cropfort Core Services standard | Y
T1-016 | Tier 1 — Core Services | Nursery | Shade Removal | bed | Cropfort Core Services standard | Y
T1-017 | Tier 1 — Core Services | Young Coffee | Hoeing (Young Coffee) | tree | Cropfort Core Services standard | Y
T1-018 | Tier 1 — Core Services | Young Coffee | Fertilizing (Young Coffee) | tree | Cropfort Core Services standard | Y
T1-019 | Tier 1 — Core Services | Young Coffee | Ring Weeding of Seedlings | tree | Cropfort Core Services standard | Y
T1-020 | Tier 1 — Core Services | Young Coffee | Shade Tree Regulation | ha | Cropfort Core Services standard | Y
T1-021 | Tier 1 — Core Services | Young Coffee | Compost Preparation | m3 | Cropfort Core Services standard | Y
T1-022 | Tier 1 — Core Services | Young Coffee | Ridge Construction | meter | Cropfort Core Services standard | Y
T1-023 | Tier 1 — Core Services | Matured Coffee | Manual Weeding | ha | Cropfort Core Services standard | Y
T1-024 | Tier 1 — Core Services | Matured Coffee | Chemical Weeding | ha | Cropfort Core Services standard | Y
T1-025 | Tier 1 — Core Services | Matured Coffee | Pruning (Matured Coffee) | tree | Cropfort Core Services standard | Y
T1-026 | Tier 1 — Core Services | Matured Coffee | Topping (Matured Coffee) | tree | Cropfort Core Services standard | Y
T1-027 | Tier 1 — Core Services | Matured Coffee | Handling and Desuckering | tree | Cropfort Core Services standard | Y
T1-028 | Tier 1 — Core Services | Matured Coffee | Coffee Tree Support/Staking | tree | Cropfort Core Services standard | Y
T1-029 | Tier 1 — Core Services | Matured Coffee | Watchman Tower (Matured Block) | tower | Cropfort Core Services standard | Y
T1-030 | Tier 1 — Core Services | Infilling | Infill Peg Preparation | planting point | Cropfort Core Services standard | Y
T1-031 | Tier 1 — Core Services | Infilling | Infill Layout and Pegging | planting point | Cropfort Core Services standard | Y
T1-032 | Tier 1 — Core Services | Infilling | Infill Hole Digging | planting point | Cropfort Core Services standard | Y
T1-033 | Tier 1 — Core Services | Infilling | Infill Hole Refilling | planting point | Cropfort Core Services standard | Y
T1-034 | Tier 1 — Core Services | Infilling | Infill Watchman Tower Prep | tower | Cropfort Core Services standard | Y
T1-035 | Tier 1 — Core Services | Infilling | Infill Seedling Transport | seedling | Cropfort Core Services standard | Y
T1-036 | Tier 1 — Core Services | Infilling | Infill Planting | seedling | Cropfort Core Services standard | Y
T1-037 | Tier 1 — Core Services | Picking & Related | Harvest Watchman Tower Prep | tower | Cropfort Core Services standard | Y
T1-038 | Tier 1 — Core Services | Picking & Related | Drying Bed Material Prep and Transport | bed | Cropfort Core Services standard | Y
T1-039 | Tier 1 — Core Services | Picking & Related | Drying Bed Site Cleaning | bed | Cropfort Core Services standard | Y
T1-040 | Tier 1 — Core Services | Picking & Related | Drying Bed Construction | bed | Cropfort Core Services standard | Y
T1-041 | Tier 1 — Core Services | Picking & Related | Selective Picking, Red Cherry | kg | Cropfort Core Services standard | Y
T1-042 | Tier 1 — Core Services | Picking & Related | Cherry Drying on Bed | bed | Cropfort Core Services standard | Y
T1-043 | Tier 1 — Core Services | Picking & Related | Drying Bed Maintenance | bed | Cropfort Core Services standard | Y
T1-044 | Tier 1 — Core Services | Picking & Related | Weighing and Arranging Dry Coffee | jute bag | Cropfort Core Services standard | Y
T1-045 | Tier 1 — Core Services | Picking & Related | Loading Dry Coffee, Farm 1 to 2 | jute bag | Cropfort Core Services standard | Y
T1-046 | Tier 1 — Core Services | Picking & Related | Loading Dry Coffee, Farm to Hulling | jute bag | Cropfort Core Services standard | Y
T1-047 | Tier 1 — Core Services | Picking & Related | Transport Vehicle Rental | jute bag | Cropfort Core Services standard | Y
T1-048 | Tier 1 — Core Services | Picking & Related | Unloading Dry Coffee at Hulling | jute bag | Cropfort Core Services standard | Y
T1-049 | Tier 1 — Core Services | Picking & Related | Hulling of Dry Coffee (incl. VAT) | jute bag | Cropfort Core Services standard | Y
T1-050 | Tier 1 — Core Services | Picking & Related | Unloading at Warehouse | quintal | Cropfort Core Services standard | Y
T1-051 | Tier 1 — Core Services | Picking & Related | Transport Clean Coffee to Addis Ababa | quintal | Cropfort Core Services standard | Y
T1-052 | Tier 1 — Core Services | Picking & Related | Drying Bed Removal | bed | Cropfort Core Services standard | Y
T2-001 | Tier 2 — Projects | A. Annual Harvest Management | Harvest Planning | farm | Cropfort Projects standard | N
T2-002 | Tier 2 — Projects | A. Annual Harvest Management | Labour Mobilisation | farm | Cropfort Projects standard | N
T2-003 | Tier 2 — Projects | A. Annual Harvest Management | Harvest Supervision | ha | Cropfort Projects standard | N
T2-004 | Tier 2 — Projects | A. Annual Harvest Management | Daily Production Monitoring | farm | Cropfort Projects standard | N
T2-005 | Tier 2 — Projects | A. Annual Harvest Management | Quality Monitoring (Harvest) | farm | Cropfort Projects standard | N
T2-006 | Tier 2 — Projects | A. Annual Harvest Management | Cherry Movement Coordination | farm | Cropfort Projects standard | N
T2-007 | Tier 2 — Projects | A. Annual Harvest Management | Daily Harvest Reporting | farm | Cropfort Projects standard | N
T2-008 | Tier 2 — Projects | A. Annual Harvest Management | Yield Reconciliation | farm | Cropfort Projects standard | N
T2-009 | Tier 2 — Projects | A. Annual Harvest Management | Harvest Close-Out | farm | Cropfort Projects standard | N
T2-010 | Tier 2 — Projects | B. Coffee Operations | Cherry Reception | farm | Cropfort Projects standard | N
T2-011 | Tier 2 — Projects | B. Coffee Operations | Washing Supervision | farm | Cropfort Projects standard | N
T2-012 | Tier 2 — Projects | B. Coffee Operations | Fermentation Supervision | farm | Cropfort Projects standard | N
T2-013 | Tier 2 — Projects | B. Coffee Operations | Drying Supervision | farm | Cropfort Projects standard | N
T2-014 | Tier 2 — Projects | B. Coffee Operations | Moisture Management | farm | Cropfort Projects standard | N
T2-015 | Tier 2 — Projects | B. Coffee Operations | Parchment Storage | farm | Cropfort Projects standard | N
T2-016 | Tier 2 — Projects | B. Coffee Operations | Warehouse Management | farm | Cropfort Projects standard | N
T2-017 | Tier 2 — Projects | B. Coffee Operations | Inventory Reconciliation | farm | Cropfort Projects standard | N
T2-018 | Tier 2 — Projects | B. Coffee Operations | Internal Transport Coordination | farm | Cropfort Projects standard | N
T2-019 | Tier 2 — Projects | B. Coffee Operations | Hulling Supervision | farm | Cropfort Projects standard | N
T2-020 | Tier 2 — Projects | B. Coffee Operations | Stock Management | farm | Cropfort Projects standard | N
T2-021 | Tier 2 — Projects | B. Coffee Operations | Loss Control | farm | Cropfort Projects standard | N
T2-022 | Tier 2 — Projects | C. Export & Commercial Operations | Export Grading Coordination | farm | Cropfort Projects standard | N
T2-023 | Tier 2 — Projects | C. Export & Commercial Operations | Quality Inspection Coordination | farm | Cropfort Projects standard | N
T2-024 | Tier 2 — Projects | C. Export & Commercial Operations | Sample Preparation | farm | Cropfort Projects standard | N
T2-025 | Tier 2 — Projects | C. Export & Commercial Operations | Client Correspondence | farm | Cropfort Projects standard | N
T2-026 | Tier 2 — Projects | C. Export & Commercial Operations | Contract Administration | farm | Cropfort Projects standard | N
T2-027 | Tier 2 — Projects | C. Export & Commercial Operations | Buyer Coordination | farm | Cropfort Projects standard | N
T2-028 | Tier 2 — Projects | C. Export & Commercial Operations | Letters of Credit Coordination | farm | Cropfort Projects standard | N
T2-029 | Tier 2 — Projects | C. Export & Commercial Operations | Export Documentation | farm | Cropfort Projects standard | N
T2-030 | Tier 2 — Projects | C. Export & Commercial Operations | Shipping Coordination | farm | Cropfort Projects standard | N
T2-031 | Tier 2 — Projects | C. Export & Commercial Operations | Export Compliance | farm | Cropfort Projects standard | N
T2-032 | Tier 2 — Projects | C. Export & Commercial Operations | Shipment Follow-Up | farm | Cropfort Projects standard | N
T2-033 | Tier 2 — Projects | C. Export & Commercial Operations | Export Proceeds Receipt and Reconciliation | farm | Cropfort Projects standard | N
T2-034 | Tier 2 — Projects | D. Asset Development | Washing Station Rehabilitation | project | Cropfort Projects standard | N
T2-035 | Tier 2 — Projects | D. Asset Development | Huller Rehabilitation | project | Cropfort Projects standard | N
T2-036 | Tier 2 — Projects | D. Asset Development | Irrigation Systems | project | Cropfort Projects standard | N
T2-037 | Tier 2 — Projects | D. Asset Development | On-Farm Water Systems Development | project | Cropfort Projects standard | N
T2-038 | Tier 2 — Projects | D. Asset Development | Roads | project | Cropfort Projects standard | N
T2-039 | Tier 2 — Projects | D. Asset Development | Buildings | project | Cropfort Projects standard | N
T2-040 | Tier 2 — Projects | D. Asset Development | Staff Housing | project | Cropfort Projects standard | N
T2-041 | Tier 2 — Projects | D. Asset Development | Workshops | project | Cropfort Projects standard | N
T2-042 | Tier 2 — Projects | D. Asset Development | Machinery Procurement | project | Cropfort Projects standard | N
T2-043 | Tier 2 — Projects | D. Asset Development | Utilities | project | Cropfort Projects standard | N
T2-044 | Tier 2 — Projects | D. Asset Development | Solar Systems (incl. Staff Welfare) | project | Cropfort Projects standard | N
T2-045 | Tier 2 — Projects | D. Asset Development | Farm Expansion | project | Cropfort Projects standard | N
T2-046 | Tier 2 — Projects | D. Asset Development | New Planting Blocks | project | Cropfort Projects standard | N
T2-047 | Tier 2 — Projects | D. Asset Development | Security Infrastructure (incl. Camp Monitoring) | project | Cropfort Projects standard | N
T3-001 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Investment Due Diligence | assignment | Cropfort Interventions standard | N
T3-002 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Technical Due Diligence | assignment | Cropfort Interventions standard | N
T3-003 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Turnaround Assessments | assignment | Cropfort Interventions standard | N
T3-004 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Strategic Reviews | assignment | Cropfort Interventions standard | N
T3-005 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Major Procurement | assignment | Cropfort Interventions standard | N
T3-006 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Organisational Reviews | assignment | Cropfort Interventions standard | N
T3-007 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Performance Audits | assignment | Cropfort Interventions standard | N
T3-008 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Recruitment Support | assignment | Cropfort Interventions standard | N
T3-009 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Regulatory Coordination and Monitoring | assignment | Cropfort Interventions standard | N
T3-010 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Security Assessments | assignment | Cropfort Interventions standard | N
T3-011 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Special Investigations | assignment | Cropfort Interventions standard | N
T3-012 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Board Reporting | assignment | Cropfort Interventions standard | N
T3-013 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Investor Reporting | assignment | Cropfort Interventions standard | N
T3-014 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Staff Capability Development | assignment | Cropfort Interventions standard | N
T3-015 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Operational Benchmarking | assignment | Cropfort Interventions standard | N
T3-016 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Feasibility Studies | assignment | Cropfort Interventions standard | N
T3-017 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Owner Representation | assignment | Cropfort Interventions standard | N
T3-018 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Coordination of Legal Advisers | assignment | Cropfort Interventions standard | N
T3-019 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Coordination of Tax Advisers | assignment | Cropfort Interventions standard | N
T3-020 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Governance Oversight | assignment | Cropfort Interventions standard | N
T3-021 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Debt Raising Support | assignment | Cropfort Interventions standard | N
T3-022 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Lender Coordination | assignment | Cropfort Interventions standard | N
T3-023 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Strategic Stakeholder Engagement | assignment | Cropfort Interventions standard | N
T3-024 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Reputation Management | assignment | Cropfort Interventions standard | N
T3-025 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Strategic Reporting | assignment | Cropfort Interventions standard | N
T3-026 | Tier 3 — Interventions | A. Institutional and Strategic Interventions | Coordination of Specialist Advisers | assignment | Cropfort Interventions standard | N
T3-027 | Tier 3 — Interventions | B. Technical and Laboratory Services | Soil Sampling and Analysis | sample | Cropfort Interventions standard | N
T3-028 | Tier 3 — Interventions | B. Technical and Laboratory Services | Soil Fertility and Nutrient Status Reporting | farm | Cropfort Interventions standard | N
T3-029 | Tier 3 — Interventions | B. Technical and Laboratory Services | Liming and Soil Amendment Recommendations | farm | Cropfort Interventions standard | N
T3-030 | Tier 3 — Interventions | B. Technical and Laboratory Services | GPS Farm Boundary and Block Mapping | farm | Cropfort Interventions standard | N
T3-031 | Tier 3 — Interventions | B. Technical and Laboratory Services | GIS Layering (Soil, Slope, Drainage, Shade, Productivity) | farm | Cropfort Interventions standard | N
T3-032 | Tier 3 — Interventions | B. Technical and Laboratory Services | Weather Station Installation and Management | farm | Cropfort Interventions standard | N
T3-033 | Tier 3 — Interventions | B. Technical and Laboratory Services | Farm Operating Manuals and SOPs | farm | Cropfort Interventions standard | N
T3-034 | Tier 3 — Interventions | B. Technical and Laboratory Services | SpiralLabs Cupping, Grading and Quality Control | farm | Cropfort Interventions standard | N
T3-035 | Tier 3 — Interventions | B. Technical and Laboratory Services | Buyer Hosting at SpiralLabs | event | Cropfort Interventions standard | N

## Master
Master — Farm and Block Registry
Farm Name:
Term Start Date (Year 1, Month 1): |  |  |  | All Annual Election windows and the per-block Calendar are calculated from this one date — set it once and everything downstream follows.
Block ID | Block Name | Hectares | Variety Planted | Planting Date | Tree Count | Status | Notes
Add one row per block. Each block also needs its own Calendar tab, generated to match.
This is the Cropfort platform template — blank on purpose. Every field here is filled in when the template is instantiated for a real farm. Adding a block row does not, on its own, create that block's Calendar tab or its Annual Election rows; those are generated to match whenever a block is added.

## Benchmark Rate Survey
Benchmark Rate Survey — Annual
Survey the piece rate paid for each activity at two adjacent farms, lock it in once entered, and let that guide — but not dictate — this farm's own rate. The recommended rate is the plain average, shown in light shade; override it in the Proposed Rate column. Nothing is binding until the mandated approver for this farm's owning company signs off, after which the rate is locked for the year.
Activity ID | Activity Name | Unit | Neighbor Farm 1 (Name) | Neighbor Farm 1 Rate (ETB/unit) | Neighbor Farm 2 (Name) | Neighbor Farm 2 Rate (ETB/unit) | Survey Locked (Y/N) | Recommended Rate (avg, light shade) | Proposed Rate (override) | Status | Approver Name | Approval Date | Valid Until | Approved Rate
T1-001 | Land Clearing | ha |  |  |  |  | N |  |  | Draft
T1-002 | Tree Felling | ha |  |  |  |  | N |  |  | Draft
T1-003 | Soil Heaping | m3 |  |  |  |  | N |  |  | Draft
T1-004 | Polytube Cutting | kg |  |  |  |  | N |  |  | Draft
T1-005 | Polytube Filling | seedling |  |  |  |  | N |  |  | Draft
T1-006 | Seedbed Preparation | bed |  |  |  |  | N |  |  | Draft
T1-007 | Polytube Arranging | bed |  |  |  |  | N |  |  | Draft
T1-008 | Seed Sowing | bed |  |  |  |  | N |  |  | Draft
T1-009 | Mulch Material Preparation | bed |  |  |  |  | N |  |  | Draft
T1-010 | Mulch Application | bed |  |  |  |  | N |  |  | Draft
T1-011 | Shade Material Preparation | bed |  |  |  |  | N |  |  | Draft
T1-012 | Shade Construction | bed |  |  |  |  | N |  |  | Draft
T1-013 | Mulch Removal | bed |  |  |  |  | N |  |  | Draft
T1-014 | Nursery Weeding | bed |  |  |  |  | N |  |  | Draft
T1-015 | Shade Thinning | bed |  |  |  |  | N |  |  | Draft
T1-016 | Shade Removal | bed |  |  |  |  | N |  |  | Draft
T1-017 | Hoeing (Young Coffee) | tree |  |  |  |  | N |  |  | Draft
T1-018 | Fertilizing (Young Coffee) | tree |  |  |  |  | N |  |  | Draft
T1-019 | Ring Weeding of Seedlings | tree |  |  |  |  | N |  |  | Draft
T1-020 | Shade Tree Regulation | ha |  |  |  |  | N |  |  | Draft
T1-021 | Compost Preparation | m3 |  |  |  |  | N |  |  | Draft
T1-022 | Ridge Construction | meter |  |  |  |  | N |  |  | Draft
T1-023 | Manual Weeding | ha |  |  |  |  | N |  |  | Draft
T1-024 | Chemical Weeding | ha |  |  |  |  | N |  |  | Draft
T1-025 | Pruning (Matured Coffee) | tree |  |  |  |  | N |  |  | Draft
T1-026 | Topping (Matured Coffee) | tree |  |  |  |  | N |  |  | Draft
T1-027 | Handling and Desuckering | tree |  |  |  |  | N |  |  | Draft
T1-028 | Coffee Tree Support/Staking | tree |  |  |  |  | N |  |  | Draft
T1-029 | Watchman Tower (Matured Block) | tower |  |  |  |  | N |  |  | Draft
T1-030 | Infill Peg Preparation | planting point |  |  |  |  | N |  |  | Draft
T1-031 | Infill Layout and Pegging | planting point |  |  |  |  | N |  |  | Draft
T1-032 | Infill Hole Digging | planting point |  |  |  |  | N |  |  | Draft
T1-033 | Infill Hole Refilling | planting point |  |  |  |  | N |  |  | Draft
T1-034 | Infill Watchman Tower Prep | tower |  |  |  |  | N |  |  | Draft
T1-035 | Infill Seedling Transport | seedling |  |  |  |  | N |  |  | Draft
T1-036 | Infill Planting | seedling |  |  |  |  | N |  |  | Draft
T1-037 | Harvest Watchman Tower Prep | tower |  |  |  |  | N |  |  | Draft
T1-038 | Drying Bed Material Prep and Transport | bed |  |  |  |  | N |  |  | Draft
T1-039 | Drying Bed Site Cleaning | bed |  |  |  |  | N |  |  | Draft
T1-040 | Drying Bed Construction | bed |  |  |  |  | N |  |  | Draft
T1-041 | Selective Picking, Red Cherry | kg |  |  |  |  | N |  |  | Draft
T1-042 | Cherry Drying on Bed | bed |  |  |  |  | N |  |  | Draft
T1-043 | Drying Bed Maintenance | bed |  |  |  |  | N |  |  | Draft
T1-044 | Weighing and Arranging Dry Coffee | jute bag |  |  |  |  | N |  |  | Draft
T1-045 | Loading Dry Coffee, Farm 1 to 2 | jute bag |  |  |  |  | N |  |  | Draft
T1-046 | Loading Dry Coffee, Farm to Hulling | jute bag |  |  |  |  | N |  |  | Draft
T1-047 | Transport Vehicle Rental | jute bag |  |  |  |  | N |  |  | Draft
T1-048 | Unloading Dry Coffee at Hulling | jute bag |  |  |  |  | N |  |  | Draft
T1-049 | Hulling of Dry Coffee (incl. VAT) | jute bag |  |  |  |  | N |  |  | Draft
T1-050 | Unloading at Warehouse | quintal |  |  |  |  | N |  |  | Draft
T1-051 | Transport Clean Coffee to Addis Ababa | quintal |  |  |  |  | N |  |  | Draft
T1-052 | Drying Bed Removal | bed |  |  |  |  | N |  |  | Draft
T2-001 | Harvest Planning | farm |  |  |  |  | N |  |  | Draft
T2-002 | Labour Mobilisation | farm |  |  |  |  | N |  |  | Draft
T2-003 | Harvest Supervision | ha |  |  |  |  | N |  |  | Draft
T2-004 | Daily Production Monitoring | farm |  |  |  |  | N |  |  | Draft
T2-005 | Quality Monitoring (Harvest) | farm |  |  |  |  | N |  |  | Draft
T2-006 | Cherry Movement Coordination | farm |  |  |  |  | N |  |  | Draft
T2-007 | Daily Harvest Reporting | farm |  |  |  |  | N |  |  | Draft
T2-008 | Yield Reconciliation | farm |  |  |  |  | N |  |  | Draft
T2-009 | Harvest Close-Out | farm |  |  |  |  | N |  |  | Draft
T2-010 | Cherry Reception | farm |  |  |  |  | N |  |  | Draft
T2-011 | Washing Supervision | farm |  |  |  |  | N |  |  | Draft
T2-012 | Fermentation Supervision | farm |  |  |  |  | N |  |  | Draft
T2-013 | Drying Supervision | farm |  |  |  |  | N |  |  | Draft
T2-014 | Moisture Management | farm |  |  |  |  | N |  |  | Draft
T2-015 | Parchment Storage | farm |  |  |  |  | N |  |  | Draft
T2-016 | Warehouse Management | farm |  |  |  |  | N |  |  | Draft
T2-017 | Inventory Reconciliation | farm |  |  |  |  | N |  |  | Draft
T2-018 | Internal Transport Coordination | farm |  |  |  |  | N |  |  | Draft
T2-019 | Hulling Supervision | farm |  |  |  |  | N |  |  | Draft
T2-020 | Stock Management | farm |  |  |  |  | N |  |  | Draft
T2-021 | Loss Control | farm |  |  |  |  | N |  |  | Draft
T2-022 | Export Grading Coordination | farm |  |  |  |  | N |  |  | Draft
T2-023 | Quality Inspection Coordination | farm |  |  |  |  | N |  |  | Draft
T2-024 | Sample Preparation | farm |  |  |  |  | N |  |  | Draft
T2-025 | Client Correspondence | farm |  |  |  |  | N |  |  | Draft
T2-026 | Contract Administration | farm |  |  |  |  | N |  |  | Draft
T2-027 | Buyer Coordination | farm |  |  |  |  | N |  |  | Draft
T2-028 | Letters of Credit Coordination | farm |  |  |  |  | N |  |  | Draft
T2-029 | Export Documentation | farm |  |  |  |  | N |  |  | Draft
T2-030 | Shipping Coordination | farm |  |  |  |  | N |  |  | Draft
T2-031 | Export Compliance | farm |  |  |  |  | N |  |  | Draft
T2-032 | Shipment Follow-Up | farm |  |  |  |  | N |  |  | Draft
T2-033 | Export Proceeds Receipt and Reconciliation | farm |  |  |  |  | N |  |  | Draft
T2-034 | Washing Station Rehabilitation | project |  |  |  |  | N |  |  | Draft
T2-035 | Huller Rehabilitation | project |  |  |  |  | N |  |  | Draft
T2-036 | Irrigation Systems | project |  |  |  |  | N |  |  | Draft
T2-037 | On-Farm Water Systems Development | project |  |  |  |  | N |  |  | Draft
T2-038 | Roads | project |  |  |  |  | N |  |  | Draft
T2-039 | Buildings | project |  |  |  |  | N |  |  | Draft
T2-040 | Staff Housing | project |  |  |  |  | N |  |  | Draft
T2-041 | Workshops | project |  |  |  |  | N |  |  | Draft
T2-042 | Machinery Procurement | project |  |  |  |  | N |  |  | Draft
T2-043 | Utilities | project |  |  |  |  | N |  |  | Draft
T2-044 | Solar Systems (incl. Staff Welfare) | project |  |  |  |  | N |  |  | Draft
T2-045 | Farm Expansion | project |  |  |  |  | N |  |  | Draft
T2-046 | New Planting Blocks | project |  |  |  |  | N |  |  | Draft
T2-047 | Security Infrastructure (incl. Camp Monitoring) | project |  |  |  |  | N |  |  | Draft
T3-001 | Investment Due Diligence | assignment |  |  |  |  | N |  |  | Draft
T3-002 | Technical Due Diligence | assignment |  |  |  |  | N |  |  | Draft
T3-003 | Turnaround Assessments | assignment |  |  |  |  | N |  |  | Draft
T3-004 | Strategic Reviews | assignment |  |  |  |  | N |  |  | Draft
T3-005 | Major Procurement | assignment |  |  |  |  | N |  |  | Draft
T3-006 | Organisational Reviews | assignment |  |  |  |  | N |  |  | Draft
T3-007 | Performance Audits | assignment |  |  |  |  | N |  |  | Draft
T3-008 | Recruitment Support | assignment |  |  |  |  | N |  |  | Draft
T3-009 | Regulatory Coordination and Monitoring | assignment |  |  |  |  | N |  |  | Draft
T3-010 | Security Assessments | assignment |  |  |  |  | N |  |  | Draft
T3-011 | Special Investigations | assignment |  |  |  |  | N |  |  | Draft
T3-012 | Board Reporting | assignment |  |  |  |  | N |  |  | Draft
T3-013 | Investor Reporting | assignment |  |  |  |  | N |  |  | Draft
T3-014 | Staff Capability Development | assignment |  |  |  |  | N |  |  | Draft
T3-015 | Operational Benchmarking | assignment |  |  |  |  | N |  |  | Draft
T3-016 | Feasibility Studies | assignment |  |  |  |  | N |  |  | Draft
T3-017 | Owner Representation | assignment |  |  |  |  | N |  |  | Draft
T3-018 | Coordination of Legal Advisers | assignment |  |  |  |  | N |  |  | Draft
T3-019 | Coordination of Tax Advisers | assignment |  |  |  |  | N |  |  | Draft
T3-020 | Governance Oversight | assignment |  |  |  |  | N |  |  | Draft
T3-021 | Debt Raising Support | assignment |  |  |  |  | N |  |  | Draft
T3-022 | Lender Coordination | assignment |  |  |  |  | N |  |  | Draft
T3-023 | Strategic Stakeholder Engagement | assignment |  |  |  |  | N |  |  | Draft
T3-024 | Reputation Management | assignment |  |  |  |  | N |  |  | Draft
T3-025 | Strategic Reporting | assignment |  |  |  |  | N |  |  | Draft
T3-026 | Coordination of Specialist Advisers | assignment |  |  |  |  | N |  |  | Draft
T3-027 | Soil Sampling and Analysis | sample |  |  |  |  | N |  |  | Draft
T3-028 | Soil Fertility and Nutrient Status Reporting | farm |  |  |  |  | N |  |  | Draft
T3-029 | Liming and Soil Amendment Recommendations | farm |  |  |  |  | N |  |  | Draft
T3-030 | GPS Farm Boundary and Block Mapping | farm |  |  |  |  | N |  |  | Draft
T3-031 | GIS Layering (Soil, Slope, Drainage, Shade, Productivity) | farm |  |  |  |  | N |  |  | Draft
T3-032 | Weather Station Installation and Management | farm |  |  |  |  | N |  |  | Draft
T3-033 | Farm Operating Manuals and SOPs | farm |  |  |  |  | N |  |  | Draft
T3-034 | SpiralLabs Cupping, Grading and Quality Control | farm |  |  |  |  | N |  |  | Draft
T3-035 | Buyer Hosting at SpiralLabs | event |  |  |  |  | N |  |  | Draft
Workflow: (1) enter both neighbor rates, set Survey Locked to Y once confirmed — treat that row's neighbor rate cells as historical from that point and do not edit them again this cycle; a fresh survey next year gets new rows, not overwritten ones. (2) Proposed Rate defaults to the Recommended average; overwrite it directly to set this farm's own figure — that replaces the link with a plain value, same convention used on the Annual Election bundle tick. (3) Set Status to 'Approved' only once the mandated approver for this farm's owning company has actually signed off — Approver Name and Approval Date are that record. (4) Approved Rate is blank until Status = Approved; the Labor Rate Card reads only this column, never Proposed Rate directly, so nothing reaches the live rate card without approval. Valid Until is one year from Approval Date; a rate can still be revised for an individual activity mid-year if a real change is decided — that revision gets its own new row, not an edit to this one, so the history stays intact.
Formulas:
Valid Until = IF([Approval Date]="","",EDATE([Approval Date],12))

## Labor Rate Card
Activity ID | Activity Name | Unit | Labor Norm (manday / unit) | Wage Rate (ETB / manday) | Computed Cost / Unit (norm x wage) | Final Labor Cost / Unit (ETB) | Status / Source
T1-001 | Land Clearing | ha |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-002 | Tree Felling | ha |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-003 | Soil Heaping | m3 |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-004 | Polytube Cutting | kg |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-005 | Polytube Filling | seedling |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-006 | Seedbed Preparation | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-007 | Polytube Arranging | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-008 | Seed Sowing | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-009 | Mulch Material Preparation | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-010 | Mulch Application | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-011 | Shade Material Preparation | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-012 | Shade Construction | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-013 | Mulch Removal | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-014 | Nursery Weeding | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-015 | Shade Thinning | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-016 | Shade Removal | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-017 | Hoeing (Young Coffee) | tree |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-018 | Fertilizing (Young Coffee) | tree |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-019 | Ring Weeding of Seedlings | tree |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-020 | Shade Tree Regulation | ha |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-021 | Compost Preparation | m3 |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-022 | Ridge Construction | meter |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-023 | Manual Weeding | ha |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-024 | Chemical Weeding | ha |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-025 | Pruning (Matured Coffee) | tree |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-026 | Topping (Matured Coffee) | tree |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-027 | Handling and Desuckering | tree |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-028 | Coffee Tree Support/Staking | tree |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-029 | Watchman Tower (Matured Block) | tower |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-030 | Infill Peg Preparation | planting point |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-031 | Infill Layout and Pegging | planting point |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-032 | Infill Hole Digging | planting point |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-033 | Infill Hole Refilling | planting point |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-034 | Infill Watchman Tower Prep | tower |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-035 | Infill Seedling Transport | seedling |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-036 | Infill Planting | seedling |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-037 | Harvest Watchman Tower Prep | tower |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-038 | Drying Bed Material Prep and Transport | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-039 | Drying Bed Site Cleaning | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-040 | Drying Bed Construction | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-041 | Selective Picking, Red Cherry | kg |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-042 | Cherry Drying on Bed | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-043 | Drying Bed Maintenance | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-044 | Weighing and Arranging Dry Coffee | jute bag |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-045 | Loading Dry Coffee, Farm 1 to 2 | jute bag |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-046 | Loading Dry Coffee, Farm to Hulling | jute bag |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-047 | Transport Vehicle Rental | jute bag |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-048 | Unloading Dry Coffee at Hulling | jute bag |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-049 | Hulling of Dry Coffee (incl. VAT) | jute bag |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-050 | Unloading at Warehouse | quintal |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-051 | Transport Clean Coffee to Addis Ababa | quintal |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T1-052 | Drying Bed Removal | bed |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-001 | Harvest Planning | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-002 | Labour Mobilisation | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-003 | Harvest Supervision | ha |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-004 | Daily Production Monitoring | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-005 | Quality Monitoring (Harvest) | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-006 | Cherry Movement Coordination | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-007 | Daily Harvest Reporting | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-008 | Yield Reconciliation | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-009 | Harvest Close-Out | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-010 | Cherry Reception | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-011 | Washing Supervision | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-012 | Fermentation Supervision | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-013 | Drying Supervision | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-014 | Moisture Management | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-015 | Parchment Storage | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-016 | Warehouse Management | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-017 | Inventory Reconciliation | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-018 | Internal Transport Coordination | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-019 | Hulling Supervision | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-020 | Stock Management | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-021 | Loss Control | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-022 | Export Grading Coordination | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-023 | Quality Inspection Coordination | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-024 | Sample Preparation | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-025 | Client Correspondence | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-026 | Contract Administration | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-027 | Buyer Coordination | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-028 | Letters of Credit Coordination | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-029 | Export Documentation | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-030 | Shipping Coordination | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-031 | Export Compliance | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-032 | Shipment Follow-Up | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-033 | Export Proceeds Receipt and Reconciliation | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-034 | Washing Station Rehabilitation | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-035 | Huller Rehabilitation | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-036 | Irrigation Systems | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-037 | On-Farm Water Systems Development | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-038 | Roads | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-039 | Buildings | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-040 | Staff Housing | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-041 | Workshops | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-042 | Machinery Procurement | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-043 | Utilities | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-044 | Solar Systems (incl. Staff Welfare) | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-045 | Farm Expansion | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-046 | New Planting Blocks | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T2-047 | Security Infrastructure (incl. Camp Monitoring) | project |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-001 | Investment Due Diligence | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-002 | Technical Due Diligence | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-003 | Turnaround Assessments | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-004 | Strategic Reviews | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-005 | Major Procurement | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-006 | Organisational Reviews | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-007 | Performance Audits | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-008 | Recruitment Support | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-009 | Regulatory Coordination and Monitoring | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-010 | Security Assessments | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-011 | Special Investigations | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-012 | Board Reporting | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-013 | Investor Reporting | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-014 | Staff Capability Development | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-015 | Operational Benchmarking | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-016 | Feasibility Studies | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-017 | Owner Representation | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-018 | Coordination of Legal Advisers | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-019 | Coordination of Tax Advisers | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-020 | Governance Oversight | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-021 | Debt Raising Support | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-022 | Lender Coordination | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-023 | Strategic Stakeholder Engagement | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-024 | Reputation Management | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-025 | Strategic Reporting | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-026 | Coordination of Specialist Advisers | assignment |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-027 | Soil Sampling and Analysis | sample |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-028 | Soil Fertility and Nutrient Status Reporting | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-029 | Liming and Soil Amendment Recommendations | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-030 | GPS Farm Boundary and Block Mapping | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-031 | GIS Layering (Soil, Slope, Drainage, Shade, Productivity) | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-032 | Weather Station Installation and Management | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-033 | Farm Operating Manuals and SOPs | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-034 | SpiralLabs Cupping, Grading and Quality Control | farm |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
T3-035 | Buyer Hosting at SpiralLabs | event |  |  | 0 | 0 | TBD — norm/wage not yet entered; or awaiting Benchmark Rate Survey approval
Final Labor Cost/Unit is what every downstream sheet reads. It takes the Benchmark Rate Survey's Approved Rate when one exists for that activity; otherwise it falls back to the norm x wage figure entered directly here. Columns D and E are for activities costed the traditional way (mandays x wage), independent of benchmarking — use whichever route applies to a given activity.

## Material Rate Card
Material ID | Material Name | Unit | Rate (ETB / unit) | Status / Source
Add one row per material input
Add one row per material input
Add one row per material input
Add one row per material input
Add one row per material input
Add one row per material input
Add one row per material input
Add one row per material input
Add one row per material input
Add one row per material input

## Outsourced Services Rate Card
Service ID | Service Name | Unit | Indicative Rate (ETB / unit) | Status / Source
Add one row per outsourced service
Add one row per outsourced service
Add one row per outsourced service
Add one row per outsourced service
Add one row per outsourced service
Add one row per outsourced service
Add one row per outsourced service
Add one row per outsourced service
Add one row per outsourced service
Add one row per outsourced service

## Fee Schedule
Fee Schedule — 3-Year Vision (36 Months)
What the farm owner pays for management, separate from the farm's own operating costs (labor, materials, services) tracked elsewhere in this workbook. Confirmed lines are guaranteed annual fees; Elective lines activate only from the month entered, per the standing election for that tier.
CONFIRMED FEE LINES (annual, guaranteed)
Core Services (Tier 1), Annual Fee
ELECTIVE FEE LINES (annual if fully elected; activates from month entered)
Elective Line | Annual Fee | Activation Month (1-36)
Tier 2 — A. Annual Harvest Management
Tier 2 — B. Coffee Operations
Tier 2 — C. Export and Commercial Operations
Tier 2 — D. Asset Development
Tier 3 — A. Institutional and Strategic Interventions
Tier 3 — B. Technical and Laboratory Services
MONTHLY SCHEDULE
Month # | Month | A. Annual Harvest Mana | B. Coffee Operations | C. Export and Commerci | D. Asset Development | A. Institutional and S | B. Technical and Labor | Confirmed | Elective Subtotal | Total Monthly Fee | Cumulative Total
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1900-01-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1900-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1900-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 1900-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 1900-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 1900-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 1900-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 1900-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 1900-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 1900-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 1900-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 1900-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 1901-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 1901-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 1901-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 1901-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 1901-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 1901-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 1901-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 1901-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 1901-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 1901-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 1901-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 1901-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 1902-01-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 1902-02-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 1902-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 1902-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1902-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 1902-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 1902-07-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 1902-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 1902-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 1902-10-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 1902-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Column headings D onward, in order, match the six Elective Fee Lines above the table. Activation Month uses the same Month # numbering as this table (1 = the month of Master's Term Start Date); a blank Activation Month means that line is never billed. This sheet is the fee Cropfort's manager invoices the farm owner — it does not include the farm's own operating costs, which are the labor, material and service budgets tracked on their own sheets and paid directly from the farm owner's Project Account.

## Annual Election
Annual Election — Year 1
Core Bundle Tick (Y elects every Tier 1 activity at once):
Tier 1 (Core): tick the bundle above to elect all at once, or overwrite an individual row's Elected cell directly to remove or add it one by one. Tier 2 (Projects) and Tier 3 (Interventions) have no bundle and no default — every row is elected individually, only once the commercial agreement for that work has been settled outside the platform.
Block ID | Activity ID | Category | Activity Name | Default Window Start | Default Window End | Planned Duration (days) | Effective End Date (auto) | Elected (Y/N)
0 | T1-001 | Nursery | Land Clearing |  |  |  |  | 0
0 | T1-002 | Nursery | Tree Felling |  |  |  |  | 0
0 | T1-003 | Nursery | Soil Heaping |  |  |  |  | 0
0 | T1-004 | Nursery | Polytube Cutting |  |  |  |  | 0
0 | T1-005 | Nursery | Polytube Filling |  |  |  |  | 0
0 | T1-006 | Nursery | Seedbed Preparation |  |  |  |  | 0
0 | T1-007 | Nursery | Polytube Arranging |  |  |  |  | 0
0 | T1-008 | Nursery | Seed Sowing |  |  |  |  | 0
0 | T1-009 | Nursery | Mulch Material Preparation |  |  |  |  | 0
0 | T1-010 | Nursery | Mulch Application |  |  |  |  | 0
0 | T1-011 | Nursery | Shade Material Preparation |  |  |  |  | 0
0 | T1-012 | Nursery | Shade Construction |  |  |  |  | 0
0 | T1-013 | Nursery | Mulch Removal |  |  |  |  | 0
0 | T1-014 | Nursery | Nursery Weeding |  |  |  |  | 0
0 | T1-015 | Nursery | Shade Thinning |  |  |  |  | 0
0 | T1-016 | Nursery | Shade Removal |  |  |  |  | 0
0 | T1-017 | Young Coffee | Hoeing (Young Coffee) |  |  |  |  | 0
0 | T1-018 | Young Coffee | Fertilizing (Young Coffee) |  |  |  |  | 0
0 | T1-019 | Young Coffee | Ring Weeding of Seedlings |  |  |  |  | 0
0 | T1-020 | Young Coffee | Shade Tree Regulation |  |  |  |  | 0
0 | T1-021 | Young Coffee | Compost Preparation |  |  |  |  | 0
0 | T1-022 | Young Coffee | Ridge Construction |  |  |  |  | 0
0 | T1-023 | Matured Coffee | Manual Weeding |  |  |  |  | 0
0 | T1-024 | Matured Coffee | Chemical Weeding |  |  |  |  | 0
0 | T1-025 | Matured Coffee | Pruning (Matured Coffee) |  |  |  |  | 0
0 | T1-026 | Matured Coffee | Topping (Matured Coffee) |  |  |  |  | 0
0 | T1-027 | Matured Coffee | Handling and Desuckering |  |  |  |  | 0
0 | T1-028 | Matured Coffee | Coffee Tree Support/Staking |  |  |  |  | 0
0 | T1-029 | Matured Coffee | Watchman Tower (Matured Block) |  |  |  |  | 0
0 | T1-030 | Infilling | Infill Peg Preparation |  |  |  |  | 0
0 | T1-031 | Infilling | Infill Layout and Pegging |  |  |  |  | 0
0 | T1-032 | Infilling | Infill Hole Digging |  |  |  |  | 0
0 | T1-033 | Infilling | Infill Hole Refilling |  |  |  |  | 0
0 | T1-034 | Infilling | Infill Watchman Tower Prep |  |  |  |  | 0
0 | T1-035 | Infilling | Infill Seedling Transport |  |  |  |  | 0
0 | T1-036 | Infilling | Infill Planting |  |  |  |  | 0
0 | T1-037 | Picking & Related | Harvest Watchman Tower Prep |  |  |  |  | 0
0 | T1-038 | Picking & Related | Drying Bed Material Prep and Transport |  |  |  |  | 0
0 | T1-039 | Picking & Related | Drying Bed Site Cleaning |  |  |  |  | 0
0 | T1-040 | Picking & Related | Drying Bed Construction |  |  |  |  | 0
0 | T1-041 | Picking & Related | Selective Picking, Red Cherry |  |  |  |  | 0
0 | T1-042 | Picking & Related | Cherry Drying on Bed |  |  |  |  | 0
0 | T1-043 | Picking & Related | Drying Bed Maintenance |  |  |  |  | 0
0 | T1-044 | Picking & Related | Weighing and Arranging Dry Coffee |  |  |  |  | 0
0 | T1-045 | Picking & Related | Loading Dry Coffee, Farm 1 to 2 |  |  |  |  | 0
0 | T1-046 | Picking & Related | Loading Dry Coffee, Farm to Hulling |  |  |  |  | 0
0 | T1-047 | Picking & Related | Transport Vehicle Rental |  |  |  |  | 0
0 | T1-048 | Picking & Related | Unloading Dry Coffee at Hulling |  |  |  |  | 0
0 | T1-049 | Picking & Related | Hulling of Dry Coffee (incl. VAT) |  |  |  |  | 0
0 | T1-050 | Picking & Related | Unloading at Warehouse |  |  |  |  | 0
0 | T1-051 | Picking & Related | Transport Clean Coffee to Addis Ababa |  |  |  |  | 0
0 | T1-052 | Picking & Related | Drying Bed Removal |  |  |  |  | 0
0 | T2-001 | A. Annual Harvest Management | Harvest Planning |  |  |  |  | N
0 | T2-002 | A. Annual Harvest Management | Labour Mobilisation |  |  |  |  | N
0 | T2-003 | A. Annual Harvest Management | Harvest Supervision |  |  |  |  | N
0 | T2-004 | A. Annual Harvest Management | Daily Production Monitoring |  |  |  |  | N
0 | T2-005 | A. Annual Harvest Management | Quality Monitoring (Harvest) |  |  |  |  | N
0 | T2-006 | A. Annual Harvest Management | Cherry Movement Coordination |  |  |  |  | N
0 | T2-007 | A. Annual Harvest Management | Daily Harvest Reporting |  |  |  |  | N
0 | T2-008 | A. Annual Harvest Management | Yield Reconciliation |  |  |  |  | N
0 | T2-009 | A. Annual Harvest Management | Harvest Close-Out |  |  |  |  | N
0 | T2-010 | B. Coffee Operations | Cherry Reception |  |  |  |  | N
0 | T2-011 | B. Coffee Operations | Washing Supervision |  |  |  |  | N
0 | T2-012 | B. Coffee Operations | Fermentation Supervision |  |  |  |  | N
0 | T2-013 | B. Coffee Operations | Drying Supervision |  |  |  |  | N
0 | T2-014 | B. Coffee Operations | Moisture Management |  |  |  |  | N
0 | T2-015 | B. Coffee Operations | Parchment Storage |  |  |  |  | N
0 | T2-016 | B. Coffee Operations | Warehouse Management |  |  |  |  | N
0 | T2-017 | B. Coffee Operations | Inventory Reconciliation |  |  |  |  | N
0 | T2-018 | B. Coffee Operations | Internal Transport Coordination |  |  |  |  | N
0 | T2-019 | B. Coffee Operations | Hulling Supervision |  |  |  |  | N
0 | T2-020 | B. Coffee Operations | Stock Management |  |  |  |  | N
0 | T2-021 | B. Coffee Operations | Loss Control |  |  |  |  | N
0 | T2-022 | C. Export & Commercial Operations | Export Grading Coordination |  |  |  |  | N
0 | T2-023 | C. Export & Commercial Operations | Quality Inspection Coordination |  |  |  |  | N
0 | T2-024 | C. Export & Commercial Operations | Sample Preparation |  |  |  |  | N
0 | T2-025 | C. Export & Commercial Operations | Client Correspondence |  |  |  |  | N
0 | T2-026 | C. Export & Commercial Operations | Contract Administration |  |  |  |  | N
0 | T2-027 | C. Export & Commercial Operations | Buyer Coordination |  |  |  |  | N
0 | T2-028 | C. Export & Commercial Operations | Letters of Credit Coordination |  |  |  |  | N
0 | T2-029 | C. Export & Commercial Operations | Export Documentation |  |  |  |  | N
0 | T2-030 | C. Export & Commercial Operations | Shipping Coordination |  |  |  |  | N
0 | T2-031 | C. Export & Commercial Operations | Export Compliance |  |  |  |  | N
0 | T2-032 | C. Export & Commercial Operations | Shipment Follow-Up |  |  |  |  | N
0 | T2-033 | C. Export & Commercial Operations | Export Proceeds Receipt and Reconciliation |  |  |  |  | N
0 | T2-034 | D. Asset Development | Washing Station Rehabilitation |  |  |  |  | N
0 | T2-035 | D. Asset Development | Huller Rehabilitation |  |  |  |  | N
0 | T2-036 | D. Asset Development | Irrigation Systems |  |  |  |  | N
0 | T2-037 | D. Asset Development | On-Farm Water Systems Development |  |  |  |  | N
0 | T2-038 | D. Asset Development | Roads |  |  |  |  | N
0 | T2-039 | D. Asset Development | Buildings |  |  |  |  | N
0 | T2-040 | D. Asset Development | Staff Housing |  |  |  |  | N
0 | T2-041 | D. Asset Development | Workshops |  |  |  |  | N
0 | T2-042 | D. Asset Development | Machinery Procurement |  |  |  |  | N
0 | T2-043 | D. Asset Development | Utilities |  |  |  |  | N
0 | T2-044 | D. Asset Development | Solar Systems (incl. Staff Welfare) |  |  |  |  | N
0 | T2-045 | D. Asset Development | Farm Expansion |  |  |  |  | N
0 | T2-046 | D. Asset Development | New Planting Blocks |  |  |  |  | N
0 | T2-047 | D. Asset Development | Security Infrastructure (incl. Camp Monitoring) |  |  |  |  | N
0 | T3-001 | A. Institutional and Strategic Interventions | Investment Due Diligence |  |  |  |  | N
0 | T3-002 | A. Institutional and Strategic Interventions | Technical Due Diligence |  |  |  |  | N
0 | T3-003 | A. Institutional and Strategic Interventions | Turnaround Assessments |  |  |  |  | N
0 | T3-004 | A. Institutional and Strategic Interventions | Strategic Reviews |  |  |  |  | N
0 | T3-005 | A. Institutional and Strategic Interventions | Major Procurement |  |  |  |  | N
0 | T3-006 | A. Institutional and Strategic Interventions | Organisational Reviews |  |  |  |  | N
0 | T3-007 | A. Institutional and Strategic Interventions | Performance Audits |  |  |  |  | N
0 | T3-008 | A. Institutional and Strategic Interventions | Recruitment Support |  |  |  |  | N
0 | T3-009 | A. Institutional and Strategic Interventions | Regulatory Coordination and Monitoring |  |  |  |  | N
0 | T3-010 | A. Institutional and Strategic Interventions | Security Assessments |  |  |  |  | N
0 | T3-011 | A. Institutional and Strategic Interventions | Special Investigations |  |  |  |  | N
0 | T3-012 | A. Institutional and Strategic Interventions | Board Reporting |  |  |  |  | N
0 | T3-013 | A. Institutional and Strategic Interventions | Investor Reporting |  |  |  |  | N
0 | T3-014 | A. Institutional and Strategic Interventions | Staff Capability Development |  |  |  |  | N
0 | T3-015 | A. Institutional and Strategic Interventions | Operational Benchmarking |  |  |  |  | N
0 | T3-016 | A. Institutional and Strategic Interventions | Feasibility Studies |  |  |  |  | N
0 | T3-017 | A. Institutional and Strategic Interventions | Owner Representation |  |  |  |  | N
0 | T3-018 | A. Institutional and Strategic Interventions | Coordination of Legal Advisers |  |  |  |  | N
0 | T3-019 | A. Institutional and Strategic Interventions | Coordination of Tax Advisers |  |  |  |  | N
0 | T3-020 | A. Institutional and Strategic Interventions | Governance Oversight |  |  |  |  | N
0 | T3-021 | A. Institutional and Strategic Interventions | Debt Raising Support |  |  |  |  | N
0 | T3-022 | A. Institutional and Strategic Interventions | Lender Coordination |  |  |  |  | N
0 | T3-023 | A. Institutional and Strategic Interventions | Strategic Stakeholder Engagement |  |  |  |  | N
0 | T3-024 | A. Institutional and Strategic Interventions | Reputation Management |  |  |  |  | N
0 | T3-025 | A. Institutional and Strategic Interventions | Strategic Reporting |  |  |  |  | N
0 | T3-026 | A. Institutional and Strategic Interventions | Coordination of Specialist Advisers |  |  |  |  | N
0 | T3-027 | B. Technical and Laboratory Services | Soil Sampling and Analysis |  |  |  |  | N
0 | T3-028 | B. Technical and Laboratory Services | Soil Fertility and Nutrient Status Reporting |  |  |  |  | N
0 | T3-029 | B. Technical and Laboratory Services | Liming and Soil Amendment Recommendations |  |  |  |  | N
0 | T3-030 | B. Technical and Laboratory Services | GPS Farm Boundary and Block Mapping |  |  |  |  | N
0 | T3-031 | B. Technical and Laboratory Services | GIS Layering (Soil, Slope, Drainage, Shade, Productivity) |  |  |  |  | N
0 | T3-032 | B. Technical and Laboratory Services | Weather Station Installation and Management |  |  |  |  | N
0 | T3-033 | B. Technical and Laboratory Services | Farm Operating Manuals and SOPs |  |  |  |  | N
0 | T3-034 | B. Technical and Laboratory Services | SpiralLabs Cupping, Grading and Quality Control |  |  |  |  | N
0 | T3-035 | B. Technical and Laboratory Services | Buyer Hosting at SpiralLabs |  |  |  |  | N
Default Window Start/End are Cropfort's suggested field-calendar timing, calculated from Master's Term Start Date — change Term Start and every window shifts with it. Planned Duration (days) is blank by default, meaning the full default window shades on the Calendar; fill it in to narrow the shading to that many days from Default Window Start (Effective End Date recalculates automatically). Asset Development and Institutional/Strategic Interventions carry no default window since they are one-off, quoted per assignment and commissioned on demand rather than calendar-driven — plan those directly on the Calendar once agreed.

## Activity Plan
Block ID | Block Name | Activity ID | Activity Name | Tier | Unit | Tick (Y/N) | Planned Qty | Labor Rate / Unit (ETB) | Planned Labor Cost (ETB) | Window Start (helper) | Window End (helper) | Weeks Spanned (helper) | Weekly Allocation (ETB, helper)
0 | 0 | T1-001 | Land Clearing | Tier 1 — Core Services | ha | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-002 | Tree Felling | Tier 1 — Core Services | ha | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-003 | Soil Heaping | Tier 1 — Core Services | m3 | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-004 | Polytube Cutting | Tier 1 — Core Services | kg | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-005 | Polytube Filling | Tier 1 — Core Services | seedling | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-006 | Seedbed Preparation | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-007 | Polytube Arranging | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-008 | Seed Sowing | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-009 | Mulch Material Preparation | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-010 | Mulch Application | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-011 | Shade Material Preparation | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-012 | Shade Construction | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-013 | Mulch Removal | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-014 | Nursery Weeding | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-015 | Shade Thinning | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-016 | Shade Removal | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-017 | Hoeing (Young Coffee) | Tier 1 — Core Services | tree | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-018 | Fertilizing (Young Coffee) | Tier 1 — Core Services | tree | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-019 | Ring Weeding of Seedlings | Tier 1 — Core Services | tree | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-020 | Shade Tree Regulation | Tier 1 — Core Services | ha | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-021 | Compost Preparation | Tier 1 — Core Services | m3 | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-022 | Ridge Construction | Tier 1 — Core Services | meter | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-023 | Manual Weeding | Tier 1 — Core Services | ha | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-024 | Chemical Weeding | Tier 1 — Core Services | ha | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-025 | Pruning (Matured Coffee) | Tier 1 — Core Services | tree | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-026 | Topping (Matured Coffee) | Tier 1 — Core Services | tree | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-027 | Handling and Desuckering | Tier 1 — Core Services | tree | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-028 | Coffee Tree Support/Staking | Tier 1 — Core Services | tree | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-029 | Watchman Tower (Matured Block) | Tier 1 — Core Services | tower | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-030 | Infill Peg Preparation | Tier 1 — Core Services | planting point | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-031 | Infill Layout and Pegging | Tier 1 — Core Services | planting point | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-032 | Infill Hole Digging | Tier 1 — Core Services | planting point | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-033 | Infill Hole Refilling | Tier 1 — Core Services | planting point | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-034 | Infill Watchman Tower Prep | Tier 1 — Core Services | tower | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-035 | Infill Seedling Transport | Tier 1 — Core Services | seedling | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-036 | Infill Planting | Tier 1 — Core Services | seedling | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-037 | Harvest Watchman Tower Prep | Tier 1 — Core Services | tower | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-038 | Drying Bed Material Prep and Transport | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-039 | Drying Bed Site Cleaning | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-040 | Drying Bed Construction | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-041 | Selective Picking, Red Cherry | Tier 1 — Core Services | kg | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-042 | Cherry Drying on Bed | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-043 | Drying Bed Maintenance | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-044 | Weighing and Arranging Dry Coffee | Tier 1 — Core Services | jute bag | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-045 | Loading Dry Coffee, Farm 1 to 2 | Tier 1 — Core Services | jute bag | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-046 | Loading Dry Coffee, Farm to Hulling | Tier 1 — Core Services | jute bag | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-047 | Transport Vehicle Rental | Tier 1 — Core Services | jute bag | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-048 | Unloading Dry Coffee at Hulling | Tier 1 — Core Services | jute bag | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-049 | Hulling of Dry Coffee (incl. VAT) | Tier 1 — Core Services | jute bag | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-050 | Unloading at Warehouse | Tier 1 — Core Services | quintal | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-051 | Transport Clean Coffee to Addis Ababa | Tier 1 — Core Services | quintal | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T1-052 | Drying Bed Removal | Tier 1 — Core Services | bed | 0 |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-001 | Harvest Planning | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-002 | Labour Mobilisation | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-003 | Harvest Supervision | Tier 2 — Projects | ha | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-004 | Daily Production Monitoring | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-005 | Quality Monitoring (Harvest) | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-006 | Cherry Movement Coordination | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-007 | Daily Harvest Reporting | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-008 | Yield Reconciliation | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-009 | Harvest Close-Out | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-010 | Cherry Reception | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-011 | Washing Supervision | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-012 | Fermentation Supervision | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-013 | Drying Supervision | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-014 | Moisture Management | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-015 | Parchment Storage | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-016 | Warehouse Management | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-017 | Inventory Reconciliation | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-018 | Internal Transport Coordination | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-019 | Hulling Supervision | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-020 | Stock Management | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-021 | Loss Control | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-022 | Export Grading Coordination | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-023 | Quality Inspection Coordination | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-024 | Sample Preparation | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-025 | Client Correspondence | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-026 | Contract Administration | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-027 | Buyer Coordination | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-028 | Letters of Credit Coordination | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-029 | Export Documentation | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-030 | Shipping Coordination | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-031 | Export Compliance | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-032 | Shipment Follow-Up | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-033 | Export Proceeds Receipt and Reconciliation | Tier 2 — Projects | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T2-034 | Washing Station Rehabilitation | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T2-035 | Huller Rehabilitation | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T2-036 | Irrigation Systems | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T2-037 | On-Farm Water Systems Development | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T2-038 | Roads | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T2-039 | Buildings | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T2-040 | Staff Housing | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T2-041 | Workshops | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T2-042 | Machinery Procurement | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T2-043 | Utilities | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T2-044 | Solar Systems (incl. Staff Welfare) | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T2-045 | Farm Expansion | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T2-046 | New Planting Blocks | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T2-047 | Security Infrastructure (incl. Camp Monitoring) | Tier 2 — Projects | project | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-001 | Investment Due Diligence | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-002 | Technical Due Diligence | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-003 | Turnaround Assessments | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-004 | Strategic Reviews | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-005 | Major Procurement | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-006 | Organisational Reviews | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-007 | Performance Audits | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-008 | Recruitment Support | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-009 | Regulatory Coordination and Monitoring | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-010 | Security Assessments | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-011 | Special Investigations | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-012 | Board Reporting | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-013 | Investor Reporting | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-014 | Staff Capability Development | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-015 | Operational Benchmarking | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-016 | Feasibility Studies | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-017 | Owner Representation | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-018 | Coordination of Legal Advisers | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-019 | Coordination of Tax Advisers | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-020 | Governance Oversight | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-021 | Debt Raising Support | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-022 | Lender Coordination | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-023 | Strategic Stakeholder Engagement | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-024 | Reputation Management | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-025 | Strategic Reporting | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-026 | Coordination of Specialist Advisers | Tier 3 — Interventions | assignment | N |  | 0 | 0 | 0 | 0 | 1 | 0
0 | 0 | T3-027 | Soil Sampling and Analysis | Tier 3 — Interventions | sample | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T3-028 | Soil Fertility and Nutrient Status Reporting | Tier 3 — Interventions | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T3-029 | Liming and Soil Amendment Recommendations | Tier 3 — Interventions | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T3-030 | GPS Farm Boundary and Block Mapping | Tier 3 — Interventions | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T3-031 | GIS Layering (Soil, Slope, Drainage, Shade, Productivity) | Tier 3 — Interventions | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T3-032 | Weather Station Installation and Management | Tier 3 — Interventions | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T3-033 | Farm Operating Manuals and SOPs | Tier 3 — Interventions | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T3-034 | SpiralLabs Cupping, Grading and Quality Control | Tier 3 — Interventions | farm | N |  | 0 | 0 |  |  |  | 0
0 | 0 | T3-035 | Buyer Hosting at SpiralLabs | Tier 3 — Interventions | event | N |  | 0 | 0 | 0 | 0 | 1 | 0
Tick (Y/N) now reads from the Annual Election sheet — election happens there first. Planned Qty is the magnitude of work for this block: how many hectares, trees, beds etc. this activity actually needs, entered once elected. Columns K-N are helper columns (window, weeks spanned, weekly allocation) feeding the Weekly Cash Flow sheet. To plan a second block: generate a matching set of Election and Activity Plan rows for that block, plus its own Calendar tab.

## Supervisor Progress
Block ID | Activity ID | Activity Name | Planned Qty | Window Start | Effective End | % Complete (25/50/75/100) | Actual Qty Done | Labor Cost Booked (ETB) | Variance Qty (Planned - Actual) | Last Movement Date (update manually when % changes) | Weeks Since Movement | Stall Flag (2+ weeks) | Rollover Qty (if window closed, <100%) | Rollover Flag | Flagged Activity (helper, for report)
0 | T1-001 | Land Clearing | 0 | [9 empty] | 0
0 | T1-002 | Tree Felling | 0 | [9 empty] | 0
0 | T1-003 | Soil Heaping | 0 | [9 empty] | 0
0 | T1-004 | Polytube Cutting | 0 | [9 empty] | 0
0 | T1-005 | Polytube Filling | 0 | [9 empty] | 0
0 | T1-006 | Seedbed Preparation | 0 | [9 empty] | 0
0 | T1-007 | Polytube Arranging | 0 | [9 empty] | 0
0 | T1-008 | Seed Sowing | 0 | [9 empty] | 0
0 | T1-009 | Mulch Material Preparation | 0 | [9 empty] | 0
0 | T1-010 | Mulch Application | 0 | [9 empty] | 0
0 | T1-011 | Shade Material Preparation | 0 | [9 empty] | 0
0 | T1-012 | Shade Construction | 0 | [9 empty] | 0
0 | T1-013 | Mulch Removal | 0 | [9 empty] | 0
0 | T1-014 | Nursery Weeding | 0 | [9 empty] | 0
0 | T1-015 | Shade Thinning | 0 | [9 empty] | 0
0 | T1-016 | Shade Removal | 0 | [9 empty] | 0
0 | T1-017 | Hoeing (Young Coffee) | 0 | [9 empty] | 0
0 | T1-018 | Fertilizing (Young Coffee) | 0 | [9 empty] | 0
0 | T1-019 | Ring Weeding of Seedlings | 0 | [9 empty] | 0
0 | T1-020 | Shade Tree Regulation | 0 | [9 empty] | 0
0 | T1-021 | Compost Preparation | 0 | [9 empty] | 0
0 | T1-022 | Ridge Construction | 0 | [9 empty] | 0
0 | T1-023 | Manual Weeding | 0 | [9 empty] | 0
0 | T1-024 | Chemical Weeding | 0 | [9 empty] | 0
0 | T1-025 | Pruning (Matured Coffee) | 0 | [9 empty] | 0
0 | T1-026 | Topping (Matured Coffee) | 0 | [9 empty] | 0
0 | T1-027 | Handling and Desuckering | 0 | [9 empty] | 0
0 | T1-028 | Coffee Tree Support/Staking | 0 | [9 empty] | 0
0 | T1-029 | Watchman Tower (Matured Block) | 0 | [9 empty] | 0
0 | T1-030 | Infill Peg Preparation | 0 | [9 empty] | 0
0 | T1-031 | Infill Layout and Pegging | 0 | [9 empty] | 0
0 | T1-032 | Infill Hole Digging | 0 | [9 empty] | 0
0 | T1-033 | Infill Hole Refilling | 0 | [9 empty] | 0
0 | T1-034 | Infill Watchman Tower Prep | 0 | [9 empty] | 0
0 | T1-035 | Infill Seedling Transport | 0 | [9 empty] | 0
0 | T1-036 | Infill Planting | 0 | [9 empty] | 0
0 | T1-037 | Harvest Watchman Tower Prep | 0 | [9 empty] | 0
0 | T1-038 | Drying Bed Material Prep and Transport | 0 | [9 empty] | 0
0 | T1-039 | Drying Bed Site Cleaning | 0 | [9 empty] | 0
0 | T1-040 | Drying Bed Construction | 0 | [9 empty] | 0
0 | T1-041 | Selective Picking, Red Cherry | 0 | [9 empty] | 0
0 | T1-042 | Cherry Drying on Bed | 0 | [9 empty] | 0
0 | T1-043 | Drying Bed Maintenance | 0 | [9 empty] | 0
0 | T1-044 | Weighing and Arranging Dry Coffee | 0 | [9 empty] | 0
0 | T1-045 | Loading Dry Coffee, Farm 1 to 2 | 0 | [9 empty] | 0
0 | T1-046 | Loading Dry Coffee, Farm to Hulling | 0 | [9 empty] | 0
0 | T1-047 | Transport Vehicle Rental | 0 | [9 empty] | 0
0 | T1-048 | Unloading Dry Coffee at Hulling | 0 | [9 empty] | 0
0 | T1-049 | Hulling of Dry Coffee (incl. VAT) | 0 | [9 empty] | 0
0 | T1-050 | Unloading at Warehouse | 0 | [9 empty] | 0
0 | T1-051 | Transport Clean Coffee to Addis Ababa | 0 | [9 empty] | 0
0 | T1-052 | Drying Bed Removal | 0 | [9 empty] | 0
0 | T2-001 | Harvest Planning | 0 | [9 empty] | 0
0 | T2-002 | Labour Mobilisation | 0 | [9 empty] | 0
0 | T2-003 | Harvest Supervision | 0 | [9 empty] | 0
0 | T2-004 | Daily Production Monitoring | 0 | [9 empty] | 0
0 | T2-005 | Quality Monitoring (Harvest) | 0 | [9 empty] | 0
0 | T2-006 | Cherry Movement Coordination | 0 | [9 empty] | 0
0 | T2-007 | Daily Harvest Reporting | 0 | [9 empty] | 0
0 | T2-008 | Yield Reconciliation | 0 | [9 empty] | 0
0 | T2-009 | Harvest Close-Out | 0 | [9 empty] | 0
0 | T2-010 | Cherry Reception | 0 | [9 empty] | 0
0 | T2-011 | Washing Supervision | 0 | [9 empty] | 0
0 | T2-012 | Fermentation Supervision | 0 | [9 empty] | 0
0 | T2-013 | Drying Supervision | 0 | [9 empty] | 0
0 | T2-014 | Moisture Management | 0 | [9 empty] | 0
0 | T2-015 | Parchment Storage | 0 | [9 empty] | 0
0 | T2-016 | Warehouse Management | 0 | [9 empty] | 0
0 | T2-017 | Inventory Reconciliation | 0 | [9 empty] | 0
0 | T2-018 | Internal Transport Coordination | 0 | [9 empty] | 0
0 | T2-019 | Hulling Supervision | 0 | [9 empty] | 0
0 | T2-020 | Stock Management | 0 | [9 empty] | 0
0 | T2-021 | Loss Control | 0 | [9 empty] | 0
0 | T2-022 | Export Grading Coordination | 0 | [9 empty] | 0
0 | T2-023 | Quality Inspection Coordination | 0 | [9 empty] | 0
0 | T2-024 | Sample Preparation | 0 | [9 empty] | 0
0 | T2-025 | Client Correspondence | 0 | [9 empty] | 0
0 | T2-026 | Contract Administration | 0 | [9 empty] | 0
0 | T2-027 | Buyer Coordination | 0 | [9 empty] | 0
0 | T2-028 | Letters of Credit Coordination | 0 | [9 empty] | 0
0 | T2-029 | Export Documentation | 0 | [9 empty] | 0
0 | T2-030 | Shipping Coordination | 0 | [9 empty] | 0
0 | T2-031 | Export Compliance | 0 | [9 empty] | 0
0 | T2-032 | Shipment Follow-Up | 0 | [9 empty] | 0
0 | T2-033 | Export Proceeds Receipt and Reconciliation | 0 | [9 empty] | 0
0 | T2-034 | Washing Station Rehabilitation | 0 | 0 | 0 | [7 empty] | 0
0 | T2-035 | Huller Rehabilitation | 0 | 0 | 0 | [7 empty] | 0
0 | T2-036 | Irrigation Systems | 0 | 0 | 0 | [7 empty] | 0
0 | T2-037 | On-Farm Water Systems Development | 0 | 0 | 0 | [7 empty] | 0
0 | T2-038 | Roads | 0 | 0 | 0 | [7 empty] | 0
0 | T2-039 | Buildings | 0 | 0 | 0 | [7 empty] | 0
0 | T2-040 | Staff Housing | 0 | 0 | 0 | [7 empty] | 0
0 | T2-041 | Workshops | 0 | 0 | 0 | [7 empty] | 0
0 | T2-042 | Machinery Procurement | 0 | 0 | 0 | [7 empty] | 0
0 | T2-043 | Utilities | 0 | 0 | 0 | [7 empty] | 0
0 | T2-044 | Solar Systems (incl. Staff Welfare) | 0 | 0 | 0 | [7 empty] | 0
0 | T2-045 | Farm Expansion | 0 | 0 | 0 | [7 empty] | 0
0 | T2-046 | New Planting Blocks | 0 | 0 | 0 | [7 empty] | 0
0 | T2-047 | Security Infrastructure (incl. Camp Monitoring) | 0 | 0 | 0 | [7 empty] | 0
0 | T3-001 | Investment Due Diligence | 0 | 0 | 0 | [7 empty] | 0
0 | T3-002 | Technical Due Diligence | 0 | 0 | 0 | [7 empty] | 0
0 | T3-003 | Turnaround Assessments | 0 | 0 | 0 | [7 empty] | 0
0 | T3-004 | Strategic Reviews | 0 | 0 | 0 | [7 empty] | 0
0 | T3-005 | Major Procurement | 0 | 0 | 0 | [7 empty] | 0
0 | T3-006 | Organisational Reviews | 0 | 0 | 0 | [7 empty] | 0
0 | T3-007 | Performance Audits | 0 | 0 | 0 | [7 empty] | 0
0 | T3-008 | Recruitment Support | 0 | 0 | 0 | [7 empty] | 0
0 | T3-009 | Regulatory Coordination and Monitoring | 0 | 0 | 0 | [7 empty] | 0
0 | T3-010 | Security Assessments | 0 | 0 | 0 | [7 empty] | 0
0 | T3-011 | Special Investigations | 0 | 0 | 0 | [7 empty] | 0
0 | T3-012 | Board Reporting | 0 | 0 | 0 | [7 empty] | 0
0 | T3-013 | Investor Reporting | 0 | 0 | 0 | [7 empty] | 0
0 | T3-014 | Staff Capability Development | 0 | 0 | 0 | [7 empty] | 0
0 | T3-015 | Operational Benchmarking | 0 | 0 | 0 | [7 empty] | 0
0 | T3-016 | Feasibility Studies | 0 | 0 | 0 | [7 empty] | 0
0 | T3-017 | Owner Representation | 0 | 0 | 0 | [7 empty] | 0
0 | T3-018 | Coordination of Legal Advisers | 0 | 0 | 0 | [7 empty] | 0
0 | T3-019 | Coordination of Tax Advisers | 0 | 0 | 0 | [7 empty] | 0
0 | T3-020 | Governance Oversight | 0 | 0 | 0 | [7 empty] | 0
0 | T3-021 | Debt Raising Support | 0 | 0 | 0 | [7 empty] | 0
0 | T3-022 | Lender Coordination | 0 | 0 | 0 | [7 empty] | 0
0 | T3-023 | Strategic Stakeholder Engagement | 0 | 0 | 0 | [7 empty] | 0
0 | T3-024 | Reputation Management | 0 | 0 | 0 | [7 empty] | 0
0 | T3-025 | Strategic Reporting | 0 | 0 | 0 | [7 empty] | 0
0 | T3-026 | Coordination of Specialist Advisers | 0 | 0 | 0 | [7 empty] | 0
0 | T3-027 | Soil Sampling and Analysis | 0 | [9 empty] | 0
0 | T3-028 | Soil Fertility and Nutrient Status Reporting | 0 | [9 empty] | 0
0 | T3-029 | Liming and Soil Amendment Recommendations | 0 | [9 empty] | 0
0 | T3-030 | GPS Farm Boundary and Block Mapping | 0 | [9 empty] | 0
0 | T3-031 | GIS Layering (Soil, Slope, Drainage, Shade, Productivity) | 0 | [9 empty] | 0
0 | T3-032 | Weather Station Installation and Management | 0 | [9 empty] | 0
0 | T3-033 | Farm Operating Manuals and SOPs | 0 | [9 empty] | 0
0 | T3-034 | SpiralLabs Cupping, Grading and Quality Control | 0 | [9 empty] | 0
0 | T3-035 | Buyer Hosting at SpiralLabs | 0 | 0 | 0 | [7 empty] | 0
% Complete is entered by the field supervisor, weekly, against the Field Ticket record — not a guess. Update Last Movement Date by hand whenever % actually changes; the Stall Flag and rollover logic both depend on that date being kept current. Rollover Qty and Rollover Flag are calculated warnings, not automatic actions — plain formulas cannot create new rows on their own, so a flagged rollover still needs a new Annual Election / Activity Plan entry created by hand for the shortfall, in the next appropriate window.
Formulas:
Rollover Qty (if window closed, <100%) = IF(AND([Effective End]<>"",TODAY()>[Effective End],OR(G2="",G2<100)),[Planned Qty]-IF([Actual Qty Done]="",0,[Actual Qty Done]),0)

## Labor Budget
Block ID | Block Name | Tier 1 — Core Services Labor Cost (ETB) | Tier 2 — Projects Labor Cost (ETB) | Tier 3 — Interventions Labor Cost (ETB) | Block Total Labor Cost (ETB)
0 | 0 | 0 | 0 | 0 | 0
| Farm Total | 0 | 0 | 0 | 0
Add a row per block as Master grows; copy the formulas across.

## Material Budget
Block ID | Activity ID | Activity Name | Material ID | Material Norm (qty / activity unit) | Material Rate (ETB / qty) | Planned Activity Qty (from Activity Plan) | Planned Material Qty | Planned Material Cost (ETB) | Window Start (helper) | Window End (helper) | Months Spanned (helper) | Monthly Allocation (ETB, helper)
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
Add one row per activity-material link, entering the Activity ID and its consumption norm. Columns J-M (Window Start/End, Months Spanned, Monthly Allocation) are helper columns feeding the Monthly Cost Summary — they read the activity's window straight from Annual Election.
Formulas:
Months Spanned (helper) = IF(OR([Window Start (helper)]="",[Window End (helper)]=""),"",DATEDIF([Window Start (helper)],[Window End (helper)],"m")+1)

## Service Budget
Block ID | Activity ID | Activity Name | Service ID | Service Norm (qty / activity unit) | Service Rate (ETB / qty) | Planned Activity Qty (from Activity Plan) | Planned Service Qty | Planned Service Cost (ETB) | Window Start (helper) | Window End (helper) | Months Spanned (helper) | Monthly Allocation (ETB, helper)
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0
Add one row per activity-service link, entering the Activity ID and its consumption norm. Columns J-M are helper columns feeding the Monthly Cost Summary.
Formulas:
Months Spanned (helper) = IF(OR([Window Start (helper)]="",[Window End (helper)]=""),"",DATEDIF([Window Start (helper)],[Window End (helper)],"m")+1)

## Monthly Cost Summary
Month # | Month | Material Cost (ETB) | Service Cost (ETB) | Total Inputs + Services (ETB)
1 |  | 0 | 0 | 0
2 |  | 0 | 0 | 0
3 |  | 0 | 0 | 0
4 |  | 0 | 0 | 0
5 |  | 0 | 0 | 0
6 |  | 0 | 0 | 0
7 |  | 0 | 0 | 0
8 |  | 0 | 0 | 0
9 |  | 0 | 0 | 0
10 |  | 0 | 0 | 0
11 |  | 0 | 0 | 0
12 |  | 0 | 0 | 0
| Year Total | 0 | 0 | 0
Each Material/Service Budget row's cost is spread evenly across the months its activity window touches (the Monthly Allocation helper column), then summed here by month. This treats materials and services as monthly figures, matching how they're actually ordered and engaged — never given a false weekly precision.
Formulas:
Material Cost (ETB) = IF([Month]="",0,SUMPRODUCT(('Material Budget'!$J2:J11<=EOMONTH([Month],0))*('Material Budget'!$K2:K11>=EOMONTH([Month],-1)+1)*'Material Budget'!$M2:M11))
Service Cost (ETB) = IF([Month]="",0,SUMPRODUCT(('Service Budget'!$J2:J11<=EOMONTH([Month],0))*('Service Budget'!$K2:K11>=EOMONTH([Month],-1)+1)*'Service Budget'!$M2:M11))

## Weekly Cash Flow
Weekly Cash Flow — Year 1
Labor is real weekly cost, prorated across each ticked activity's own window. Inputs and services are monthly figures (Monthly Cost Summary) split evenly across the weeks that fall in each month — an honest cash-flow allocation, not fabricated weekly precision. Use the cumulative column to size the Project Account reserve.
Week # | Week Start | Week End | Labor Cost (ETB) | Inputs + Services Cost (ETB) | Total Weekly Cost (ETB) | Cumulative Total (ETB)
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
4 |  |  | 0 | 0 | 0 | 0
5 |  |  | 0 | 0 | 0 | 0
6 |  |  | 0 | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 | 0
8 |  |  | 0 | 0 | 0 | 0
9 |  |  | 0 | 0 | 0 | 0
10 |  |  | 0 | 0 | 0 | 0
11 |  |  | 0 | 0 | 0 | 0
12 |  |  | 0 | 0 | 0 | 0
13 |  |  | 0 | 0 | 0 | 0
14 |  |  | 0 | 0 | 0 | 0
15 |  |  | 0 | 0 | 0 | 0
16 |  |  | 0 | 0 | 0 | 0
17 |  |  | 0 | 0 | 0 | 0
18 |  |  | 0 | 0 | 0 | 0
19 |  |  | 0 | 0 | 0 | 0
20 |  |  | 0 | 0 | 0 | 0
21 |  |  | 0 | 0 | 0 | 0
22 |  |  | 0 | 0 | 0 | 0
23 |  |  | 0 | 0 | 0 | 0
24 |  |  | 0 | 0 | 0 | 0
25 |  |  | 0 | 0 | 0 | 0
26 |  |  | 0 | 0 | 0 | 0
27 |  |  | 0 | 0 | 0 | 0
28 |  |  | 0 | 0 | 0 | 0
29 |  |  | 0 | 0 | 0 | 0
30 |  |  | 0 | 0 | 0 | 0
31 |  |  | 0 | 0 | 0 | 0
32 |  |  | 0 | 0 | 0 | 0
33 |  |  | 0 | 0 | 0 | 0
34 |  |  | 0 | 0 | 0 | 0
35 |  |  | 0 | 0 | 0 | 0
36 |  |  | 0 | 0 | 0 | 0
37 |  |  | 0 | 0 | 0 | 0
38 |  |  | 0 | 0 | 0 | 0
39 |  |  | 0 | 0 | 0 | 0
40 |  |  | 0 | 0 | 0 | 0
41 |  |  | 0 | 0 | 0 | 0
42 |  |  | 0 | 0 | 0 | 0
43 |  |  | 0 | 0 | 0 | 0
44 |  |  | 0 | 0 | 0 | 0
45 |  |  | 0 | 0 | 0 | 0
46 |  |  | 0 | 0 | 0 | 0
47 |  |  | 0 | 0 | 0 | 0
48 |  |  | 0 | 0 | 0 | 0
49 |  |  | 0 | 0 | 0 | 0
50 |  |  | 0 | 0 | 0 | 0
51 |  |  | 0 | 0 | 0 | 0
52 |  |  | 0 | 0 | 0 | 0
53 |  |  | 0 | 0 | 0 | 0
53 weeks covers the 365-day year with the last week short by a few days. If Term Start is blank, every row reads zero — set Master's Term Start Date first. Column E's self-reference (COUNTIFS against this sheet's own Week Start column) counts how many weeks fall in that same calendar month, so the monthly total splits evenly across them.

## Total Budget Summary
Total Budget Summary
Block ID | Block Name | Labor Budget (ETB) | Material Budget (ETB) | Service Budget (ETB) | Total Budget (ETB)
0 | 0 | 0 | 0 | 0 | 0
| Farm Total | 0 | 0 | 0 | 0
By Tier
Tier | Labor Budget (ETB) | Material Budget (ETB) | Service Budget (ETB) | Total (ETB)
Tier 1 — Core Services | 0 | 0 | 0 | 0
Tier 2 — Projects | 0 | 0 | 0 | 0
Tier 3 — Interventions | 0 | 0 | 0 | 0
Grand Total | 0 | 0 | 0 | 0
This is the farm's own operating cost — labor, materials and services paid from the farm owner's Project Account. It is separate from the Fee Schedule, which is what the farm owner pays Cropfort's manager for running this program.

## Calendar - Block 1
Calendar - Block 1 — Year 1 (365 days from Term Start)
Shading reads live off the Annual Election sheet for this block — elect the Core bundle or an individual activity there, and its row shades automatically here for the duration assigned. If Master's Term Start Date is blank, the day headers below will show blank/zero until it's set.
Block ID | Activity ID | Activity Name | Category | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1900-01-31 | 1900-02-01 | 1900-02-02 | 1900-02-03 | 1900-02-04 | 1900-02-05 | 1900-02-06 | 1900-02-07 | 1900-02-08 | 1900-02-09 | 1900-02-10 | 1900-02-11 | 1900-02-12 | 1900-02-13 | 1900-02-14 | 1900-02-15 | 1900-02-16 | 1900-02-17 | 1900-02-18 | 1900-02-19 | 1900-02-20 | 1900-02-21 | 1900-02-22 | 1900-02-23 | 1900-02-24 | 1900-02-25 | 1900-02-26 | 1900-02-27 | 1900-02-28 | 1900-03-01 | 1900-03-02 | 1900-03-03 | 1900-03-04 | 1900-03-05 | 1900-03-06 | 1900-03-07 | 1900-03-08 | 1900-03-09 | 1900-03-10 | 1900-03-11 | 1900-03-12 | 1900-03-13 | 1900-03-14 | 1900-03-15 | 1900-03-16 | 1900-03-17 | 1900-03-18 | 1900-03-19 | 1900-03-20 | 1900-03-21 | 1900-03-22 | 1900-03-23 | 1900-03-24 | 1900-03-25 | 1900-03-26 | 1900-03-27 | 1900-03-28 | 1900-03-29 | 1900-03-30 | 1900-03-31 | 1900-04-01 | 1900-04-02 | 1900-04-03 | 1900-04-04 | 1900-04-05 | 1900-04-06 | 1900-04-07 | 1900-04-08 | 1900-04-09 | 1900-04-10 | 1900-04-11 | 1900-04-12 | 1900-04-13 | 1900-04-14 | 1900-04-15 | 1900-04-16 | 1900-04-17 | 1900-04-18 | 1900-04-19 | 1900-04-20 | 1900-04-21 | 1900-04-22 | 1900-04-23 | 1900-04-24 | 1900-04-25 | 1900-04-26 | 1900-04-27 | 1900-04-28 | 1900-04-29 | 1900-04-30 | 1900-05-01 | 1900-05-02 | 1900-05-03 | 1900-05-04 | 1900-05-05 | 1900-05-06 | 1900-05-07 | 1900-05-08 | 1900-05-09 | 1900-05-10 | 1900-05-11 | 1900-05-12 | 1900-05-13 | 1900-05-14 | 1900-05-15 | 1900-05-16 | 1900-05-17 | 1900-05-18 | 1900-05-19 | 1900-05-20 | 1900-05-21 | 1900-05-22 | 1900-05-23 | 1900-05-24 | 1900-05-25 | 1900-05-26 | 1900-05-27 | 1900-05-28 | 1900-05-29 | 1900-05-30 | 1900-05-31 | 1900-06-01 | 1900-06-02 | 1900-06-03 | 1900-06-04 | 1900-06-05 | 1900-06-06 | 1900-06-07 | 1900-06-08 | 1900-06-09 | 1900-06-10 | 1900-06-11 | 1900-06-12 | 1900-06-13 | 1900-06-14 | 1900-06-15 | 1900-06-16 | 1900-06-17 | 1900-06-18 | 1900-06-19 | 1900-06-20 | 1900-06-21 | 1900-06-22 | 1900-06-23 | 1900-06-24 | 1900-06-25 | 1900-06-26 | 1900-06-27 | 1900-06-28 | 1900-06-29 | 1900-06-30 | 1900-07-01 | 1900-07-02 | 1900-07-03 | 1900-07-04 | 1900-07-05 | 1900-07-06 | 1900-07-07 | 1900-07-08 | 1900-07-09 | 1900-07-10 | 1900-07-11 | 1900-07-12 | 1900-07-13 | 1900-07-14 | 1900-07-15 | 1900-07-16 | 1900-07-17 | 1900-07-18 | 1900-07-19 | 1900-07-20 | 1900-07-21 | 1900-07-22 | 1900-07-23 | 1900-07-24 | 1900-07-25 | 1900-07-26 | 1900-07-27 | 1900-07-28 | 1900-07-29 | 1900-07-30 | 1900-07-31 | 1900-08-01 | 1900-08-02 | 1900-08-03 | 1900-08-04 | 1900-08-05 | 1900-08-06 | 1900-08-07 | 1900-08-08 | 1900-08-09 | 1900-08-10 | 1900-08-11 | 1900-08-12 | 1900-08-13 | 1900-08-14 | 1900-08-15 | 1900-08-16 | 1900-08-17 | 1900-08-18 | 1900-08-19 | 1900-08-20 | 1900-08-21 | 1900-08-22 | 1900-08-23 | 1900-08-24 | 1900-08-25 | 1900-08-26 | 1900-08-27 | 1900-08-28 | 1900-08-29 | 1900-08-30 | 1900-08-31 | 1900-09-01 | 1900-09-02 | 1900-09-03 | 1900-09-04 | 1900-09-05 | 1900-09-06 | 1900-09-07 | 1900-09-08 | 1900-09-09 | 1900-09-10 | 1900-09-11 | 1900-09-12 | 1900-09-13 | 1900-09-14 | 1900-09-15 | 1900-09-16 | 1900-09-17 | 1900-09-18 | 1900-09-19 | 1900-09-20 | 1900-09-21 | 1900-09-22 | 1900-09-23 | 1900-09-24 | 1900-09-25 | 1900-09-26 | 1900-09-27 | 1900-09-28 | 1900-09-29 | 1900-09-30 | 1900-10-01 | 1900-10-02 | 1900-10-03 | 1900-10-04 | 1900-10-05 | 1900-10-06 | 1900-10-07 | 1900-10-08 | 1900-10-09 | 1900-10-10 | 1900-10-11 | 1900-10-12 | 1900-10-13 | 1900-10-14 | 1900-10-15 | 1900-10-16 | 1900-10-17 | 1900-10-18 | 1900-10-19 | 1900-10-20 | 1900-10-21 | 1900-10-22 | 1900-10-23 | 1900-10-24 | 1900-10-25 | 1900-10-26 | 1900-10-27 | 1900-10-28 | 1900-10-29 | 1900-10-30 | 1900-10-31 | 1900-11-01 | 1900-11-02 | 1900-11-03 | 1900-11-04 | 1900-11-05 | 1900-11-06 | 1900-11-07 | 1900-11-08 | 1900-11-09 | 1900-11-10 | 1900-11-11 | 1900-11-12 | 1900-11-13 | 1900-11-14 | 1900-11-15 | 1900-11-16 | 1900-11-17 | 1900-11-18 | 1900-11-19 | 1900-11-20 | 1900-11-21 | 1900-11-22 | 1900-11-23 | 1900-11-24 | 1900-11-25 | 1900-11-26 | 1900-11-27 | 1900-11-28 | 1900-11-29 | 1900-11-30 | 1900-12-01 | 1900-12-02 | 1900-12-03 | 1900-12-04 | 1900-12-05 | 1900-12-06 | 1900-12-07 | 1900-12-08 | 1900-12-09 | 1900-12-10 | 1900-12-11 | 1900-12-12 | 1900-12-13 | 1900-12-14 | 1900-12-15 | 1900-12-16 | 1900-12-17 | 1900-12-18 | 1900-12-19 | 1900-12-20 | 1900-12-21 | 1900-12-22 | 1900-12-23 | 1900-12-24 | 1900-12-25 | 1900-12-26 | 1900-12-27 | 1900-12-28 | 1900-12-29
0 | T1-001 | Land Clearing | Nursery
0 | T1-002 | Tree Felling | Nursery
0 | T1-003 | Soil Heaping | Nursery
0 | T1-004 | Polytube Cutting | Nursery
0 | T1-005 | Polytube Filling | Nursery
0 | T1-006 | Seedbed Preparation | Nursery
0 | T1-007 | Polytube Arranging | Nursery
0 | T1-008 | Seed Sowing | Nursery
0 | T1-009 | Mulch Material Preparation | Nursery
0 | T1-010 | Mulch Application | Nursery
0 | T1-011 | Shade Material Preparation | Nursery
0 | T1-012 | Shade Construction | Nursery
0 | T1-013 | Mulch Removal | Nursery
0 | T1-014 | Nursery Weeding | Nursery
0 | T1-015 | Shade Thinning | Nursery
0 | T1-016 | Shade Removal | Nursery
0 | T1-017 | Hoeing (Young Coffee) | Young Coffee
0 | T1-018 | Fertilizing (Young Coffee) | Young Coffee
0 | T1-019 | Ring Weeding of Seedlings | Young Coffee
0 | T1-020 | Shade Tree Regulation | Young Coffee
0 | T1-021 | Compost Preparation | Young Coffee
0 | T1-022 | Ridge Construction | Young Coffee
0 | T1-023 | Manual Weeding | Matured Coffee
0 | T1-024 | Chemical Weeding | Matured Coffee
0 | T1-025 | Pruning (Matured Coffee) | Matured Coffee
0 | T1-026 | Topping (Matured Coffee) | Matured Coffee
0 | T1-027 | Handling and Desuckering | Matured Coffee
0 | T1-028 | Coffee Tree Support/Staking | Matured Coffee
0 | T1-029 | Watchman Tower (Matured Block) | Matured Coffee
0 | T1-030 | Infill Peg Preparation | Infilling
0 | T1-031 | Infill Layout and Pegging | Infilling
0 | T1-032 | Infill Hole Digging | Infilling
0 | T1-033 | Infill Hole Refilling | Infilling
0 | T1-034 | Infill Watchman Tower Prep | Infilling
0 | T1-035 | Infill Seedling Transport | Infilling
0 | T1-036 | Infill Planting | Infilling
0 | T1-037 | Harvest Watchman Tower Prep | Picking & Related
0 | T1-038 | Drying Bed Material Prep and Transport | Picking & Related
0 | T1-039 | Drying Bed Site Cleaning | Picking & Related
0 | T1-040 | Drying Bed Construction | Picking & Related
0 | T1-041 | Selective Picking, Red Cherry | Picking & Related
0 | T1-042 | Cherry Drying on Bed | Picking & Related
0 | T1-043 | Drying Bed Maintenance | Picking & Related
0 | T1-044 | Weighing and Arranging Dry Coffee | Picking & Related
0 | T1-045 | Loading Dry Coffee, Farm 1 to 2 | Picking & Related
0 | T1-046 | Loading Dry Coffee, Farm to Hulling | Picking & Related
0 | T1-047 | Transport Vehicle Rental | Picking & Related
0 | T1-048 | Unloading Dry Coffee at Hulling | Picking & Related
0 | T1-049 | Hulling of Dry Coffee (incl. VAT) | Picking & Related
0 | T1-050 | Unloading at Warehouse | Picking & Related
0 | T1-051 | Transport Clean Coffee to Addis Ababa | Picking & Related
0 | T1-052 | Drying Bed Removal | Picking & Related
0 | T2-001 | Harvest Planning | A. Annual Harvest Management
0 | T2-002 | Labour Mobilisation | A. Annual Harvest Management
0 | T2-003 | Harvest Supervision | A. Annual Harvest Management
0 | T2-004 | Daily Production Monitoring | A. Annual Harvest Management
0 | T2-005 | Quality Monitoring (Harvest) | A. Annual Harvest Management
0 | T2-006 | Cherry Movement Coordination | A. Annual Harvest Management
0 | T2-007 | Daily Harvest Reporting | A. Annual Harvest Management
0 | T2-008 | Yield Reconciliation | A. Annual Harvest Management
0 | T2-009 | Harvest Close-Out | A. Annual Harvest Management
0 | T2-010 | Cherry Reception | B. Coffee Operations
0 | T2-011 | Washing Supervision | B. Coffee Operations
0 | T2-012 | Fermentation Supervision | B. Coffee Operations
0 | T2-013 | Drying Supervision | B. Coffee Operations
0 | T2-014 | Moisture Management | B. Coffee Operations
0 | T2-015 | Parchment Storage | B. Coffee Operations
0 | T2-016 | Warehouse Management | B. Coffee Operations
0 | T2-017 | Inventory Reconciliation | B. Coffee Operations
0 | T2-018 | Internal Transport Coordination | B. Coffee Operations
0 | T2-019 | Hulling Supervision | B. Coffee Operations
0 | T2-020 | Stock Management | B. Coffee Operations
0 | T2-021 | Loss Control | B. Coffee Operations
0 | T2-022 | Export Grading Coordination | C. Export & Commercial Operations
0 | T2-023 | Quality Inspection Coordination | C. Export & Commercial Operations
0 | T2-024 | Sample Preparation | C. Export & Commercial Operations
0 | T2-025 | Client Correspondence | C. Export & Commercial Operations
0 | T2-026 | Contract Administration | C. Export & Commercial Operations
0 | T2-027 | Buyer Coordination | C. Export & Commercial Operations
0 | T2-028 | Letters of Credit Coordination | C. Export & Commercial Operations
0 | T2-029 | Export Documentation | C. Export & Commercial Operations
0 | T2-030 | Shipping Coordination | C. Export & Commercial Operations
0 | T2-031 | Export Compliance | C. Export & Commercial Operations
0 | T2-032 | Shipment Follow-Up | C. Export & Commercial Operations
0 | T2-033 | Export Proceeds Receipt and Reconciliation | C. Export & Commercial Operations
0 | T2-034 | Washing Station Rehabilitation | D. Asset Development
0 | T2-035 | Huller Rehabilitation | D. Asset Development
0 | T2-036 | Irrigation Systems | D. Asset Development
0 | T2-037 | On-Farm Water Systems Development | D. Asset Development
0 | T2-038 | Roads | D. Asset Development
0 | T2-039 | Buildings | D. Asset Development
0 | T2-040 | Staff Housing | D. Asset Development
0 | T2-041 | Workshops | D. Asset Development
0 | T2-042 | Machinery Procurement | D. Asset Development
0 | T2-043 | Utilities | D. Asset Development
0 | T2-044 | Solar Systems (incl. Staff Welfare) | D. Asset Development
0 | T2-045 | Farm Expansion | D. Asset Development
0 | T2-046 | New Planting Blocks | D. Asset Development
0 | T2-047 | Security Infrastructure (incl. Camp Monitoring) | D. Asset Development
0 | T3-001 | Investment Due Diligence | A. Institutional and Strategic Interventions
0 | T3-002 | Technical Due Diligence | A. Institutional and Strategic Interventions
0 | T3-003 | Turnaround Assessments | A. Institutional and Strategic Interventions
0 | T3-004 | Strategic Reviews | A. Institutional and Strategic Interventions
0 | T3-005 | Major Procurement | A. Institutional and Strategic Interventions
0 | T3-006 | Organisational Reviews | A. Institutional and Strategic Interventions
0 | T3-007 | Performance Audits | A. Institutional and Strategic Interventions
0 | T3-008 | Recruitment Support | A. Institutional and Strategic Interventions
0 | T3-009 | Regulatory Coordination and Monitoring | A. Institutional and Strategic Interventions
0 | T3-010 | Security Assessments | A. Institutional and Strategic Interventions
0 | T3-011 | Special Investigations | A. Institutional and Strategic Interventions
0 | T3-012 | Board Reporting | A. Institutional and Strategic Interventions
0 | T3-013 | Investor Reporting | A. Institutional and Strategic Interventions
0 | T3-014 | Staff Capability Development | A. Institutional and Strategic Interventions
0 | T3-015 | Operational Benchmarking | A. Institutional and Strategic Interventions
0 | T3-016 | Feasibility Studies | A. Institutional and Strategic Interventions
0 | T3-017 | Owner Representation | A. Institutional and Strategic Interventions
0 | T3-018 | Coordination of Legal Advisers | A. Institutional and Strategic Interventions
0 | T3-019 | Coordination of Tax Advisers | A. Institutional and Strategic Interventions
0 | T3-020 | Governance Oversight | A. Institutional and Strategic Interventions
0 | T3-021 | Debt Raising Support | A. Institutional and Strategic Interventions
0 | T3-022 | Lender Coordination | A. Institutional and Strategic Interventions
0 | T3-023 | Strategic Stakeholder Engagement | A. Institutional and Strategic Interventions
0 | T3-024 | Reputation Management | A. Institutional and Strategic Interventions
0 | T3-025 | Strategic Reporting | A. Institutional and Strategic Interventions
0 | T3-026 | Coordination of Specialist Advisers | A. Institutional and Strategic Interventions
0 | T3-027 | Soil Sampling and Analysis | B. Technical and Laboratory Services
0 | T3-028 | Soil Fertility and Nutrient Status Reporting | B. Technical and Laboratory Services
0 | T3-029 | Liming and Soil Amendment Recommendations | B. Technical and Laboratory Services
0 | T3-030 | GPS Farm Boundary and Block Mapping | B. Technical and Laboratory Services
0 | T3-031 | GIS Layering (Soil, Slope, Drainage, Shade, Productivity) | B. Technical and Laboratory Services
0 | T3-032 | Weather Station Installation and Management | B. Technical and Laboratory Services
0 | T3-033 | Farm Operating Manuals and SOPs | B. Technical and Laboratory Services
0 | T3-034 | SpiralLabs Cupping, Grading and Quality Control | B. Technical and Laboratory Services
0 | T3-035 | Buyer Hosting at SpiralLabs | B. Technical and Laboratory Services
Shading is generated by conditional formatting reading the Annual Election sheet, so it updates live as ticks, windows and Planned Duration change there. Activities with no default window never auto-shade; plan those manually once agreed.

## Monthly Client Report
Monthly Report — [Farm Name] — [Reporting Month]
Prepared under the Cropfort Process Assurance Protocol™. This sheet pulls its figures from the live operating data on the other sheets — it is a summary layer, not a separate record.
1. EXECUTIVE SUMMARY
% of Year 1 Plan Complete
Total Budget (ETB) | 0
Actual Labor Cost Booked to Date (ETB) | 0
Activities Flagged At Risk | 0
Activities Rolled Over | 0
Narrative (one or two lines, entered by the supervisor/manager each month):
2. PROGRESS VS. PLAN, BY TIER
Tier | Planned Qty (sum) | Actual Qty Done (sum) | % Complete (avg)
Tier 1 — Core Services | 0 | 0
Tier 2 — Projects | 0 | 0
Tier 3 — Interventions | 0 | 0
3. BUDGET VS. ACTUAL
| Labor | Material | Service | Total
Budget (ETB) | 0 | 0 | 0 | 0
Actual to Date (ETB) | 0 |  |  | 0
4. RISK REGISTER
Auto-flagged count (from Supervisor Progress, "AT RISK"), see Executive Summary above.
None currently flagged.
Other risks / open AFEs (manual):
5. LOOK-AHEAD, NEXT MONTH
See the relevant month band on the block Calendar tab(s) for exact shaded activities.
6. FIELD OBSERVATIONS
7. ASSURANCE NOTE
This report is prepared by Cropfort's manager under the Cropfort Process Assurance Protocol™ — a documented field methodology addressing rigor and traceability, aligned with the principles of internationally recognized coffee-sustainability standards, without itself constituting certification. The dashboard figures above are the manager's own reporting and should be read as such, not as independent proof: a manager validating its own work is not, by itself, verification. Independent assurance comes from three channels: (1) audit-trail and drill-down rights to the underlying Annual Farm Program / Authorization for Expenditure / Work Order / Field Ticket chain, available on request; (2) externally verifiable facts — yield against the baseline assessment, export volumes and revenue, and any third-party certification audits; (3) the farm owner's own independent oversight channel, which sits entirely outside this reporting pipeline.